REPUBLIC OF RWANDA

NATIONAL INSTITUTE OF

STATISTICS OF RWANDA

P.O BOX 6139 KIGALI-RWANDA

E-mail : info@statistics.gov.rw

Website: www.statistics.gov.rw

Name of the procuring entity:  National Institute of Statistics of Rwanda (NISR)

FORMAT OF THE MONTHLY PROGRESS REPORT FOR THE EXECUTION OF THE PROCUREMENT PLAN (article 10 of Ministerial order Nº 001/08/10/MIN of 15/01/2008 establishing regulations on public procurement and standard bidding documents)

Covered period                      :  From 1st July 2012 to 30th June 2013

Monthly progress report       :   April 2013

Type of tender                     :    Goods and non consulting Services

| Nº | Tender reference No | Title of the tender | Estimated Budget in Rwf | Status | Planned Procurement method | Procurement method used | Source of funds | Actual date of publication | Actual date starting contracting execution | Contract amount in Rwf | Contract period: | Execution progress status in % | Date of Goods inspection & acceptance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | ### 107/S/12/RfQ/CENSUS UNIT/NISR | ### JULY 2012: ### Closer User Group Communication fees in order to develop and implement the mobile phones communication system during the listing of household and census data collection for the period starting 4th Aug. to 4th Sept.2012 | 25,000,000 | Execution | Request For Quotation addressed to all telecommunication companies | RfQ | UNFPA Budget | 15th June 2012 | 30th July 2012 | 17,192,310 | 30 days | 100% | 4/09/12 |
|  |  | Total of tenders awarded in July 2012 |  |  |  |  |  |  |  | 17,192,310 |  |  |  |
| 2. | ### 083/S/2012/RFP/DDG | ### August 2012: Maintenance of NISR building ( small works) | 8,400,000 | Execution | NCB | NCB | Ordinary Budget | 25th March 2012 | 01st October 2012 | (13,216,000) -2,285,223 (7 jerrycans of paint, super sol, placing curtains,etc) -818,920 (7 toilets and other materials) -212,400 -181,720 -359,900 -236,000 -463,740 | 2 years | 40% | October 2014 31/8/12 24/9/12 19/10/12 19/10/12 5/11/12 5/11/12 4/12/12 |
| 3. | ### NO 089/F/2012-NO/DDG’S OFFICE/DA UNIT/NISR /ORDINARY BUDGET AND OTHER BUDGETS ALLOCATED TO NISR | ### Two (2) years contract for supply of office stationeries and field work materials and equipments. | 166,500,000 (NISR procurement plan 2011-2012) | Execution | NCB | NCB | Ordinary budget and all budgets allocated to NISR | 25th March 2012 | 28th June 2012 | (Two years contract based on unit prices, purchase order is given on period basis as below) - 1,125,000; - 84,000 - 626,380 - 4,265,350 -105,459,500; - 966,100; -931,200; -1,754,400 - 1,252,000 - 1,115,500 | 2 years contract | 45% | June 2014 5/9/12 5/9/12 15/9/12 - - 24/9/12 17/10/12 12/12/12 14/2/13 28/3/13 |
| 4 | 031/F/2011-NO/DDG/NISR/BASKETCFUND AND OTHER BUDGETS ALLOCATED TO NISR | Printing all NISR documents such as Census questionnaires and enumerator’s manuals, brochures, other manuals. Books, reports, profiles | 114,000 (NISR World Bank and General Procurement Plans) | Execution | NCB | NCB | NSDS Basket Fund + ALL OTHER BUDGETS | 07th September 2012 | 30th December 2011 | (Two years contract based on unit prices, purchase order is given on period basis as below) - 234,968 -1,899,949 -8,516,468 -2,093,040 -482,443 -7,148,860 -141,895 -5,842,487 -3,973,296 -442,500 -6,111,928 -132,160 -881,460 -1,533,056 -8,244,660 -998,280 -1,593,000 -5,540,171 | 2 years 3 days 5 days 3 days 3 days 5 days 5 days 3 days | 67% | 30th December 2013 31/8/12 31/8/12 31/8/12 31/8/12 17/9/12 12/9/12 21/9/12 26/11/12 20/11/12 6/11/12 9/11/12 28/12/12 27/12/12 18/12/12 18/12/12 18/1/13 3/1/13 11/4/13 |
| 6 | 109/F/2012-NO/DA UNIT/NISR/BF | Supply of insurance for 38 vehicles used in the field by NISR | 3,300,000 | Execution | NCB | NCB | NSDS Basket Fund | 21/6/12 and 26/6/12-addendum | 10/8/12 | 4,668,540 | One year | 100 | 09/8/13 |
| 7 | 043/S/2010/NO/DDDG’S OFFICE | Hotel facility in Kigali City for meeting, workshops, seminars, training, exam sessions, general staff meetings, etc. MEDIUM LEVEL | - | Execution | NCB | NCB | Ordinary budget | 22nd Dec. 2010 | 30th March 2011 Contract renewed for one year from 30th march 2012 to 30th March 2013 | (One year contract based on unit prices, purchase order is given on period basis as below) - 467,200 - 998,000 - 998,000 - 892,000 - 272,000 -1,154,000 -7,553,600 -104,200 -850,000 -280,000 -494,000 -1,612,800 - 1,008,000 - 990,000 - 158,900 - 2,000,000 | One Year (this contract was renewed 1 day 1 day 1 day 1 day 1 day 2 days 3 days 1 day 1day 1day 1day 1day 1 week 1 day I day 1 day | 60% | March 2013 7/8/12 13/8/12 21/8/12 27/8/12 29/8/12 7/9/12 14/9/12 8/11/12 31/8/12 12/11/12 07/12/12 14/2/13 11/3/13 7/3/13 15/4/13 30/4/13 |
|  |  | Total of tenders awarded in August 2012 |  |  |  |  |  |  |  | 137,824,638 |  |  |  |
|  |  | September 2012 |  |  |  |  |  |  |  |  |  |  |  |
| 8 | 050/F/2010/NO/DDG’S OFFICE/NISR | Printing of business cards, invitation cards, badges, visitor’s cards, stamps, etc- Contract renewed from 26th April 2012 to 30th April 2013 | - | Execution | NCB | NCB | Ordinary Budget | 22nd Dec. 2010 | 26th March 2011 | (One year contract based on unit prices, purchase order is given on period basis as below) -181,720 -59,000 -230,100 -70,000 -23,600 -79,650 -29,382 - 761,100 | One Year 5 days 3 days |  | 26th March 2013 17/9/12 8/9/12 03/10/12 14/11/12 18/12/12 24/4/13 10/4/13 5/10/12 |
| 9 | 009/F/2012FSMRP UNIT/NISR/NSDS BF | Supply of User Group service for 150 Persons for the 2012 PHC Post Enumeration Survey | 900,000 | Execution | RfQ | RfQ | NSDS Basket Fund | 07TH Sep. 2012 | 13th Sept 2012 | - 900,000 | One month | 100 | 14 Oct. 2012 |
| 10 | 007/F/2012/RFQ/NISR/DES UNIT/BF | Supply of 3 External Hard Disks of 2TB and 40 SD memory cards 4GB for the National Agricultural Survey | -1,230,000 | Execution | Request For Quotation | RFQ | NSDS Basket Fund | 30th August 2012 | 13th Sep. 2012 | - 649,590 | 7 days | 100 | 25/9/12 |
| 11 | 008/F/2012/RFQ/NISR/DES UNIT/BF | Supply of 60 Magnifying glasses for the National Agricultural Survey | 300,000 | Execution | Request For Quotation | RFQ | NSDS Basket Fund | 30th August 2012 | 13th Sep. 2012 | - 552,240 | 7 days | 100 | 25/9/12 |
| 12 | 042/S/2010/DDG’S OFFICE/ALL BUDGETS | Hotel facility in Musanze District for meeting, workshops, seminars, training, exam sessions, general staff meetings, etc. Contract renewed from 28th April 2012 to 30th April 2013 | - | Execution | NCB | NCB | ALL BUDGETS | 22nd Dec. 2010 | 27th April 2011/ Contract renewed for one year from 37th April 2012 to 26th April 2013 | (One year contract based on unit prices, purchase order is given on period basis as below) -1,309,000 -37,299,000 -105,000 -90,000 -90,000 - 120,000 -27,934,000 | One year contract 5 days 5 days | 100% | 26th April 2013 24/10/12 15/11/12 9/11/12 30/1/13 19/3/13 21/3/13 |
|  |  | Total tenders awarded end of September 2012 (In Rwf) |  |  |  |  |  |  |  | 11,424,748 |  |  |  |
|  |  | Total cumulative up to the end of September 2012 (In Rwf) |  |  |  |  |  |  |  | 166,441,696 |  |  |  |
|  |  | October 2012 |  |  |  |  |  |  |  |  |  |  |  |
| 13 | 089/F/2012/NO/ALL UNITS/NSDS BF & ALL BUDGETS | Hotel facility in Kigali City for 2 years contract 2012-2013 for meeting, workshops, seminars, training, exam sessions, general staff meetings, etc. VIP LEVEL | - | Execution | NCB | NCB | NSDS BF AND OTHER BUDGETS | 23rd May 2012 | 27TH June 2012 | (Two years contract based on unit prices, purchase order is given on period basis as below) - 15,426,000 - 341,000 -5,916,800 -91,900 -414,500 -10,510,000 - 262,000 - 295,500 | 2 years | 25% | 26th June 2014 9/10/12 22/10/12 30/10/12 2/11/12 28/11/12 15/1/13 03/2/13 14/3/13 |
| 14 | 088/F/2012-NO/DDG/DA/NISR | Supply of ink cartridges, toners for printers and photocopiers used by NISR for 2 years | - | Execution | NCB | NCB | All NISR Budgets | 25th March 2012 | 01st October 2012 | -1,560,000 -7,640,000 -16,542,000 - 390,000 | 2 Years | 29% | 01st October 2014 9/10/12 8/11/12 8/11/12 14/2/13 |
| 15 | 107/F/NISR/2012 | Insurance of field workers during the surveys organized by NISR. | 70,000,000 | Cancel led | NCB | NCB | All NISR Budgets | 21/6/12 23/6/12 (addendum) | - | Framework contract | 5 years | 0 | Tender cancelled |
| 16 | 109/F/NISR/2012 | Publication of NISR tenders, articles, announcements, etc. in regional and international newspapers | - | Tendering | NCB | NCB | All NISR Budgets | 21/6/12 23/6/12 (addendum) | - | Framework contract | 5 years | 0 | - |
| 17 | 110/F/NISR/2012 | Acquisition and maintenance of three (3) fax machines. | 1,700,000 | Tendering | NCB | NCB | All NISR Budgets | 21/6/12 23/6/12 (addendum) | 13/12/12 | 4,035,000 | 10 days delivery 1 year maintenance | 0 |  |
| 18 | 111/F/NISR/2012 | Supply of cafeteria consumables for NISR Staff | 25,000,000 | Tendering | NCB | NCB | All NISR Budgets | 21/6/12 23/6/12 (addendum) | 1/12/12 | Framework contract -468,540 -748,875 -1,337,931 -977,314 -1,004,935 | 2 years | 2% | Nov 2014 22/11/12 17/12/12 Feb 13 6/3/13 29/4/13 |
| 19 | 112/F/NISR/2012 | Realization and production of publicity spots on radio and TV for sensitization. | - | Tendering | NCB | NCB | All NISR Budgets | 21/6/12 23/6/12 (addendum) | Contracting process now | Framework contract | 2 years | 0 | - |
| 21 | 114/F/NISR/2012 | Event management to cater for decoration services, cultural troupe, audio-video production, camera service, supply albums and production of photos and other related services during events organized by NISR. | - | Tendering | NCB | NCB | All NISR Budgets | 21/6/12 23/6/12 (addendum) | Contracting process now | Framework contract | 2 years | 0 | - |
| 22 | 115/F/NISR/2012 | Sourcing a specialized restaurant based in Kigali City for catering service at NISR conference rooms during the meeting and workshops organized by NISR. | - | Tendering | NCB | NCB | All NISR Budgets | 21/6/12 23/6/12 (addendum) | Contract signed on 09th November 2012 | Framework contract - 32,000 - 528,000 | 2 years | 0 | - 19/2/13 23/4/13 |
| 23 | 004/F/2012-2013/NO/MIS UNIT/NISR/NSDS BF | Supply and installation of air conditioners (ACs) as additional materials in the data entry and codification rooms for the upcoming 2012 Rwanda population and housing | 13,620,000 | Tendering | NCB | NCB | All NISR Budgets | 24th August 2012 | Final notification of tender award now | 10,077,200 | 1 year Maintenance | 0 | - |
|  |  | Total tenders awarded end of October 2012 (In Rwf) |  |  |  |  |  |  |  | 83,764,020 |  |  |  |
| 24 | 042/S/2010/NO/ALL UNITS/NSDS BF & ALL BUDGETS | Hotel facility in Karongi District, for 1 year contract for meeting, workshops, seminars, training, exam sessions, general staff meetings, etc. | - | Execution | NCB | Contract renewed until April 2013 | NSDS BF AND OTHER BUDGETS | - | - | (One year contract based on unit prices, purchase order is given on period basis as below) - 250,000 | 1 years |  | 30th April 2013 2/11/12 |
|  |  | Total tenders awarded end of November 2012 (In Rwf) |  |  |  |  |  |  |  | 43,872,251 |  |  |  |
| 25 | 124/S/2011-2012/DC/SMRP UNIT/NISR/NSDS BF | Total tenders awarded/reported in December 2012 (In Rwf) PUBLICATION OF ONE PAGE CONTENTS IN THE COMMONWEALTH YEAR BOOK 2012 | 13,530 GBP= 13,030,984 Rwf | executed | DC (SSS) | DC (SSS) | NSDS Basket Fund | - | 10th April 2012 | 13,782,482 | 2 months | 100% | April 2012 |
| 26 | 096/F/2012-NO/RFQ/CENSUS UNIT/NISR | Hiring of a recording room for producing a CD for census mater trainers to be used during the cascading of census functionalities at all levels of trainings | 1 Million | Execution | RfQ | RfQ | GoR | - | - | 900,000 | 7 days | 100% | May 2012 |
|  |  | Total tenders awarded/reported in December 2012 (In Rwf) |  |  |  |  |  |  |  | 28,958,433 |  |  |  |
|  |  | Total cumulative up to the end of December 2012 (In Rwf) |  |  |  |  |  |  |  | 323,036,400 |  |  |  |
| 27 | 013/F/ 2012-2013/DG’s OFFICE/NISR/NSDS BASKET FUND SUPPORT TO NISR | Tenders awarded in January 2013 Supply of 56 Frames and 56 certificates to be given to Institutions that supported NISR in 2012PHC | 1,000,000 | executed | RfQ | RfQ | NSDS BF | - | - | 991,200 | 7Days | 100 | 03/01/13 |
| 28 | 021/RfQ/ICT UNIT/NISR/NSDS BASKET FUND/IT accessories | Supply of IT accessories for data entry and processing rooms | 1,000,000 | executed | RfQ | RfQ | NSDS BF | - | - | 613,000 | 7 days | 100 | 05/01/13 |
| 29 | 113/F/2012-NO/DA UNIT/NISR/NSDS BASKET FUND | SOURCING SPORTS SERVICES FOR NISR STAFF FOR A PERIOD OF TWO (2) YEARS | Framework contract 2 yrs | Execution | NCB | NCB | NSDS BF | 21/6/12 | 9/11/12 | 3,465,000 | 2 years | 30 | Nov 2014 |
| 30 | 067/S/2012/MIS/ALL BUDGETS | Maintenance of NISR ICT Equipments for 2 Years | Framework contract 2 yrs |  | NCB | NCB | NSDS BF | 11/2/12 | 1/10/12 | 438,750 213,438 250,632 239,540 | 15days | 35 | Oct 2014 Feb 13 March 13 Idem idem |
|  |  | Total tenders awarded/reported in January 2013 (In Rwf) |  |  |  |  |  |  |  | 20,037161 |  |  |  |
| 31 | 023/RTM/DA 2012-2013/DA UNIT/NISR/NSDS BASKET FUND-Insurance for 20 new Pick-ups | TENDERS awarded/reported in February 2013 Insurance of 20 NISR vehicles | 2,000,000 | Executed | NCB | RTM | NSDS BF | Invitation Letter | 18/2/13 | 1,956,200 | One Year | 100% (paid in advance) | 17/2/2014 |
| 32 | 014/S/2012-2013-NO/DDG’S OFFICE/DA UNIT/NISR/ALL NISR BUDGETS. | Maintenance of all NISR Vehicles for two (2) years | 108,000,000 | Execution | NCB | NCB | NSDS BF | 04th December 2012 | 15/2/13 | Frame work contract of 2 years -1,108,982 -1,175,522 -781,066 -1,108,982 -18,290 -123,310 | 2 years | 5% | 14/2/15 1/3/13 1/3/13 1/3/13 1/3/13 1/3/13 8/3/13 |
| 33 | 015/S/2012-2013-NO/DDG’S OFFICE/DA UNIT/NISR/ALL NISR BUDGETS | Security services to NISR for a period of two (2) years |  | Execution | NCB | NCB | All NISR Budgets | 04th December 2012 | March 2013 not yet signed but in process | Rwf 47,860,800 (1,994,200 Rwf every month) | 2 years | 4% | March 2015 |
| 34 | 023/F/2012-2013/DA UNIT/NISR/NS SDBASKET FUND | Supply of fuel and gasoil to NISR for a period of two years | 75,000,000*2 |  | NCB | NCB | NSDS BF | 11TH January 2013 | 26/2/13 | Frame work contract of 2 years - 6,500,000 - 9,202,000 - 8,462,000 | 2 years | 8% | 25/2/13 28/2/13 21/03/13 25/04/13 |
| 35 | 042/S/2010/NO/DDG’S OFFICE/ALL BUDGETS | Hotel facility in Rwamagana District, for 1 year contract for meeting, workshops, seminars, training, exam sessions, general staff meetings, etc. | - | Execution | NCB | Contract renewed until April 2013 | NSDS BF AND OTHER BUDGETS | - | - | (One year contract based on unit prices, purchase order is given on period basis as below) - 200,000 | 1 years | 100 | 30th April 2013 14/2/13 |
| 36 | 030/RFQ/2012-2013/NO/UCT UNIT/NISR/NSDS BF | TENDERS awarded/reported in March 2013 Supply of cleaning materials | 1,000,000 | Eecuted | RFQ | RFQ | NSDS BF | 11/3/13 | Purchase Order 18/4/13 | 588,600 | - | 100 | materials delivered on 19/04/13 |
| 37 | Nr.022/RfQ/2012-2013/NO/DG’s OFFICE/ NISR/ORDINARY BUDGET | Supply of DG Fridge, carpets, door mats, | 1,000,000 | Execution | RFQ | RFQ | GOR | 28th December 2012 | Purchase Order waiting | 735,140 | - | 0 | - |
| 38 | 024/RFQ/DES UNIT/NISR/NSDS BASKET FUND | Supply of 60 scale rulers | 1,000,000 | Execution | RFQ | RFQ | NSDS BF | 12th Feb 2013 | Purchase Order done | 390,000 | - | 100 | Materials delivered on 02/4/13 |
| 39 | 026/RFQ/DES UNIT/NISR/NSDS BASKET FUND | Supply of changeover switch for the generator + installation | 1,000,000 | Execution | RFQ | RFQ | NSDS BF | 22nd Feb 2013 | Purchase Order waiting | 830,130 | - | 100 | - |
| 40 | 027/RFQ/DES UNIT/NISR/NSDS BASKET FUND | Reactivation of Short code used in 2012 PHC to be used in Rapid SMS project/service provider RURA | 1,000,000 | Execution | SSS | SSS | NSDS BF | Letter adressed to RURA on 01st April 2012 | Purchase Order | 126,000 | - | 100 | Short Code reactivated April 2013 |
|  |  | Total amount of tenders awarded during the month of March 2013 |  |  |  |  |  |  |  | 40,129,946 |  |  |  |
| 41 | RFQ 028/2012-2013/RT/ICT UNIT/NISR/NSDS BF | Tenders awarded during the month of April 2013: Supply of 16 modems to be used by top management staff of NISR and one year wires internet subscription | 3,840,000 | Tendering | Restricted tendering | Restricted tendering | NSDS BF | 22nd March 2013 | May 2013 | 2,880,000 Waiting for Purchase Order | One year | 0 | May 2013 |
| 42 | 037/NCS/2012-2013/CENSUS UNIT/NISR/ORDINARY BUDGET/ | Renewal of the contract related to hiring space for storage and archiving of 2012 PHC materials | 93,189,600 | Execution | NOCB | SSS | NSDS BF and other Budgets | Contract renewed | 24th April 2013 | 97,690,944 | One Year | 0% | 24/4/2013 |
| 43 | 025/RFQ/2012-2013/DES UNIT/NSDSD BF | SUPLLY OF 50 MEDICAL TOOL KITS | 750,000 | Executed | RfQ | RFQ | NSDS BF | 22nd March 2013 | Purchase Order | 988,500 | Direct delivery | 100 | First week of May 2013 |
| 44 | 033/RFQ/ ICT UNIT /NISR/NSDS BASKET FUND/SUPPLY OF 60 PAIRS OF BATTERIES | Supply of 60 Batteries (alkaline cells) to be used to be used in electronic scales used by price data collectors | 240,000 | Executed | RfQ | RFQ | NSDS BF | 01st March 2013 | Purchase order done on 3/4/13 | 210,000 | Direct delivery | 100 | Goods delivered |
| 45 | 036/SSS/2012-2013/DA UNIT/NISR/ORDINARY BUDGET/PUBLICATION OF NISR NOTICES IN IMVAHO NSHYA | Broadcast on radio Rwanda as well as community radios and on Rwanda television: “documentaries, live talk show, town meeting and announcements” and to “publish NISR announcements in Imvaho Nshya newspaper. | 5,000,000 | Execution | SSS | SSS | GoR | March 2013 | 04/4/13 | Frame work contract, NISR will give a purchase order to ORINFOR on regular basis depending on NISR needs; -295,000 -165,200 -283,200 | One year with a possibility of renewal | 8% | 18/4/13 1/4/13 12/4/13 |
| 46 | 038/SSS/2012-2013/DA UNIT/NISR/ ORDINARY BUDGET | Publication NISR adverts, notices, …in one of wide circulation newspaper | 5,000,000 |  | SSS | SSS | GoR | Feb 2013 | 01/3/13 | Frame work contract, NISR will give a purchase order to New Times on regular basis depending on NISR needs; -470,820 - 237,180 -237,180 | One year with a possibility of renewal | 17% | 18/4/13 1/4/13 3/4/13 |
|  |  | Total of tenders awarded in April 2013 + Purchase Orders given on regular basis for framework contracts |  |  |  |  |  |  |  | 131,224,162 |  |  |  |
|  |  | Total cumulative up to the end of April 2013 (In Rwf) |  |  |  |  |  |  |  | 574,493,469 |  |  |  |

Done at Kigali, on 13th May 2013

Prepared by:                                                                                                      	Approved by:

Alphonse SHUMBUSHO				         	Odette MBABAZI

Procurement Officer/NISR                                                                          	Deputy Director General of Corporate Services

This is a framework contract of two years, NISR paying 550,667 Rwf/month of retainer fee but GECO can also invoice spare parts replaced agreed upon by both parties and following contractual obligations.

This refers to hotel facilitation for 164 participants (trainers &enumerators) for 2012 Population and Housing Census Post Enumeration Survey. This activity was conducted from 12th to 14th September 2012 at la Palisse Nyandungu Hotel and was not reported in the progress report of the mount of September.

This expenditure was consumed in August 2012 but it was not report in August 2012 progress report.

This purchase order was made in October 2012 but was not reported

This tender was cancelled due to the fact that NISR will affiliate all field workers to RSSB

The tendering process for this tender was suspended for internal reasons and it will be put in the FY 2013-2014 Procurement plan and budgets

The tendering process for this tender was suspended for internal reasons and it will be put in the FY 2013-2014 Procurement plan and budgets

The exchange rate on the contract date 30th April 2012 is  1 GBP= 963,117808 Rwf (average exchange rate BNR: www.bnr.gov.rw)

This tender was awarded on 08th February 2012 but not reported in FY2011-2012 due to delay of the Service Provider to send his Final Invoice on 16th April 2012 and due also to budget constraints of NISR at that particular time. NISR has been able to pay this invoice on 14th December 2012.

The exchange rate of 14th December 2012, payment date is 1 GBP= 1018,660908 Rwf.

This Tender was awarded on 15th May 2012 but due to administrative issues it was not reported in FY 2011-2012, Purchase Order is done in December 2012.

This refers to first installment of annual fee related to top management

This refers to spare part of server

We will report all amounts related to periodic purchase orders given to the successful bidder

We will report all amounts related to periodic purchase orders given to the successful bidder

This amount was paid in March 2013 but no reported

This tender is suspended due to internal reasons, and it will be put in the procurement plan and budgets of FY 2012-2013

This tender is suspended due to internal reasons, and it will be put in the procurement plan and budgets of FY 2012-2013

The difference between the previous and recent contract amounts is due to the increase of exchange rate Rwf/USD