REPUBLIC OF RWANDA

NATIONAL INSTITUTE OF

STATISTICS OF RWANDA

P.O BOX 6139 KIGALI-RWANDA

E-mail : info@statistics.gov.rw

Website: www.statistics.gov.rw

Name of the procuring entity:  National Institute of Statistics of Rwanda (NISR)

FORMAT OF THE MONTHLY PROGRESS REPORT FOR THE EXECUTION OF THE PROCUREMENT PLAN (article 10 of Ministerial order Nº 001/08/10/MIN of 15/01/2008 establishing regulations on public procurement and standard bidding documents)

Covered period                      :  From 1st July 2012 to 30th June 2013

Monthly progress report       :   August 2012

Type of tender                     :    Goods

| Nº | Title of the tender | Size of the tender | Tendering method or Procurement method | Source of funds | Date planned for the publication or Tentative date for publication | Real date of publication or Actual date for the publication | Date planned for the beginning of the execution of the contract or Planed date for starting contract execution | Real date of the beginning of the execution of the contract or Actual date for starting contract execution | Estimated cost of the contract (In Rwf) or Contract amount | Completion period of delivery or Delivery period | Execution progress status in % | Date of completion of works, Goods delivery period or Approval of consultant service final report |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | ### JULY 2012: ### Closer User Group Communication fees in order to develop and implement the mobile phones communication system during the listing of household and census data collection for the period starting 4th Aug. to 4th Sept.2012 | User Group for 4,358 beneficiaries | Request For Quotation addressed to all telecommunication companies | UNFPA Budget | - | - | 30/7/12 | 2/8/12 | 17,192,310 | 30 days | 100% | 4/09/12 |
|  | Total of tenders awarded in July 2012 |  |  |  |  |  |  |  | 17,192,310 |  |  |  |
| 2. | ### August 2012: Maintenance of NISR building ( small works) | 7 jerrycans of paint, super sol, placing curtains,etc. | National Open Tender | Ordinary Budget | - | - | 1/6/12 | 1/6/12 | 2,285,223 | 15 days | 90% | 31/8/12 |
| 3 | ### Acquisition of 7 toilets and other materials. | 7 toilets | Request For Quotation | Ordinary Budget | - | - | 16/8/12 | 31/8/12 | 818,920 | 15 days | 80% | - |
| 4 | ### Two (2) years contract for supply of office stationeries and field work materials and equipments. | Office materials and field materials | National Open Tender | NSDS Basket Fund | 28/2/12 | 25/3/12 | 15/6/12 | 28/6/12 | - 1,125,000; - 84,000 - 626,380 - 4,265,350 -105,459,500; - 966,100; | 7 days 7 days 25 days 25 days 25 days 25 days | 100 100 80% 80% 80% 80% | 5/9/12 5/9/12 - - - - |
| 5 | Printing all NISR documents such as Census questionnaires and enumerator’s manuals, brochures, other manuals. | One year contract | National Open Method | NSDS Basket Fund | 25th March 2010 | 28t March 2010 | 10/8/11 | 18/8/11 | - 234,968 -1,899,949 -8,516,468 -2,093,040 | 3 days 5 days 3 days 3 days | 100 100 100 100 | 31/8/12 31/8/12 31/8/12 31/8/12 |
| 6 | Supply of insurance for 38 vehicles used in the field by NISR | 38 vehicles | National Open Method | NSDS Basket Fund | 15/6/12 | 21/6/12 | 31/7/12 | 10/8/12 | 4,668,540 | 3 days | 100 | 13/8/12 |
| 7 | Hotel facility in Kigali City for meeting, workshops, seminars, training, exam sessions, general staff meetings, etc. | One year renewable | National Open Tender | Ordinary budget | 20th Dec. 2010 | 22nd Dec. 2010 | 15th March 2011 | 29th March 2011 | - 467,200 - 998,000 - 998,000 - 892,000 - 272,000 -1,154,000 | 1 day 1 day 1 day 1 day 1 day 2 days | 100 100 100 100 100 100 | 7/8/12 13/8/12 21/8/12 27/8/12 29/8/12 7/9/12 |
|  | Total of tenders awarded in August 2012 |  |  |  |  |  |  |  | 137,824,638 |  |  |  |
|  | Total cumulative up to the end of August 2012 (In Rwf) |  |  |  |  |  |  |  | 155,016,948 |  |  |  |

Done at Kigali, on 13/09/2012

Prepared by:                                                                                                      Approved by:

Eric BUGINGO				                    Odette MBABAZI

Procurement Officer/NISR                                                                          Deputy Director General of Corporate Services