REPUBLIC OF RWANDA

NATIONAL INSTITUTE OF STATISTICS OF RWANDA

P.O BOX 6139 KIGALI-RWANDA

E-mail : info@statistics.gov.rw

Website: www.statistics.gov.rw

Name of the procuring entity :  National Institute of Statistics of Rwanda (NISR)

FORMAT OF THE MONTHLY PROGRESS REPORT FOR THE EXECUTION OF THE PROCUREMENT PLAN (Article 10 of Ministerial Order Nº 001/08/10/MIN of 15/01/2008 establishing regulations on Public Procurement and Standard Bidding Documents)

Covered financial year           :  From 31st July 2012 to 30th June 2013

Covered period                      :  July 2012

Type of tender                      :  SERVICE

| No | Title of the tender | Size of the tender | Tendering method or Procurement method | Source of funds | Date planned for the publication or Tentative date for publication | Real date of publication or Actual date for the publication | Date planned for the beginning of the execution of the contract or Planed date for starting contract execution | Real date of the beginning of the execution of the contract or Actual date for starting contract execution | Estimated cost of the contract (In Rfw) or Contract amount | Completion period of delivery or Delivery period | Execution progress status in % | Date of completion of works, delivery period or Approval of consultant service final report |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Tenders awarded in July 2012: | - | - | - | - | - | - | - | - | - | - | - |
| 1. | Recruitment of consulting firm to develop and implement mobile phones/rapid SMS system in order to improve data collection and dissemination activities at NISR. | 6 months | International open tender/CQBS | NSDS Basket Fund | 18th June 2011 | 21th June 2011 | 31st August 2012 | Not yet | Not yet. Still in the evaluation of technical proposals submitted by the companies. | December 2012 | 30% | Planned in December 2012 |
| 2. | Seeking for a local or international firm to develop a strategy for developing a modern statistical information centre including a library of NISR. | 1 year | International open tender/Request of EOI | NSDS Basket Fund | 18th June 2011 | 21th June 2011 | 31st August 2012 | Not yet | Not yet. Still in the evaluation of technical proposals submitted by the consulting firms. | May 2013 | 25% | Planned in the end of May 2013 |
| 3. | Seeking an international consultant to provide an independent yet informed view about the state of affairs of the first NSDS1 implementation and the appropriateness of proposed NSDS1 activities to be funded from the NSDS1 Basket Fund | From 13th to 31st August 2012 | International Individual Consultant | NSDS Basket Fund | 7th June 2012 | 10th June 2012 | 01st August 2012 | 3rd August 2012 | Rwf 13,631,000 | 18 days | 100% | 31st August 2012 |
| 4. | Recruitment of international individual consultant sampling expert and provide the capacity building in sampling theory including the preparation of interim EICV3. | July 2012 to December 2014 | International open tender/Individual consultant | NSDS Basket Fund | 18th June 2011 | 21th June 2011 | 31st July 2012 | Not yet | Not yet. Still in the evaluation of applications submitted by the consultants. | December 2014 | 25% | To be completed in December 2014 |
| 5. | Recruitment of international individual consultant data processing expert to improve NISR survey data processing and archiving systems and capacity building. | July 2012 to December 2014 | International open tender/Individual consultant | NSDS Basket Fund | 18th June 2011 | 21th June 2011 | 31st July 2012 | Not yet | Not yet. Still in the evaluation of applications submitted by the consultants. | December 2014 | 25% | To be completed in December 2014 |
|  | Total amount of tenders awarded/ July 2012 |  |  |  |  |  |  |  | Rwf 13,631,000 |  |  |  |
|  | Total amount cumulative ( In Rwf) from July 2012 to the end of June 2013 |  |  |  |  |  |  |  | Rwf 13,631,000 |  |  |  |

Done at Kigali, on 14/08/2012

Prepared by:                                                                                                     Approved by:

Eric BUGINGO                                                                                                   Odette MBABAZI

Procurement Officer/NISR                                                                          Deputy Director General of Corporate Services