REPUBLIC OF RWANDA

NATIONAL INSTITUTE OF STATISTICS OF RWANDA

P.O BOX 6139 KIGALI-RWANDA

E-mail : info@statistics.gov.rw

Website: www.statistics.gov.rw

Name of the Procuring Entity:  National Institute of Statistics of Rwanda (NISR)

FORMAT OF THE MONTHLY PROGRESS REPORT FOR THE EXECUTION OF THE PROCUREMENT PLAN (Article 10 of Ministerial Order Nº 001/08/10/MIN of 15/01/2008 establishing regulations on Public Procurement and Standard Bidding Documents)

Covered financial year           :  From 31st July 2012 to 30th June 2013

Covered period                      :  November 2012

Type of tender                      :  SERVICES

| No | Tender reference | Title of the tender | Estimated budget | Status | Planned Procurement method | Procurement method used | Source of funds | Actual date of publication | Actual date of starting contracting | Contract amount | Contract period | Execution progress status in % | Date of completion of works, delivery period or Approval of consultant service final report |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Tenders awarded in July-November 2012: |  |  |  |  |  |  |  |  |  |  |  |
| 1. | RfP NO 105/S/2012/SMRP/NSDS BF | Recruitment of consulting firm to develop and implement mobile phones/rapid SMS system in order to improve data collection and dissemination activities at NISR. | 6 months | Execution | National open tender/CQBS | NCB | NSDS Basket Fund | 21st June 2012 | 02nd October 2012 | 14,160,000 | 60 days | 70% | 31st December 2012 |
| 2. | RfP NO 104/S/2012/SMRP/NSDS BF | Seeking for a local or international firm to develop a strategy for developing a modern statistical information centre including a library of NISR. | 1 year | In evaluation | International open tender/Request of EOI | ICB | NSDS Basket Fund | 21st June 2012 | Not yet | The process for this tender was stopped due to the reason that it is financed by World Bank after procurement plan is approved. Now it is done and RfP together with ToR have to be sent to WB for review | 12 months | 35% | - |
| 3. | RfP NO 105/S/2012/DES/NSDS BF | Seeking an international consultant to provide an independent yet informed view about the state of affairs of the first NSDS1 implementation and the appropriateness of proposed NSDS1 activities to be funded from the NSDS1 Basket Fund | From 13th to 31st August 2012 | Execution | International Individual Consultant |  | NSDS Basket Fund | 7th June 2012 | 10th June 2012 | Rwf 13,631,000 | 18 Men-days | 100% | 30th October 2012 |
| 4. | RfP NO 105/S/2012/MIS/NSDS BF | Recruitment of international individual consultant sampling expert and provide the capacity building in sampling theory including the preparation of interim EICV3. | July 2012 to December 2014 | Financial evaluation ongoing | International open tender/Individual consultant | ICB | NSDS Basket Fund | 18th June 2011 | 21th June 2011 | Technical & Financial Proposals now sent by the Consultant, Evaluation will be finalized after point of view of end user Unit SMRP | 6 months | 0% | - |
| 5. | RfP NO 101/S/2012/MIS/NSDS BF | Recruitment of international individual consultant data processing expert to improve NISR survey data processing and archiving systems and capacity building. | July 2012 to December 2014 |  | International open tender/Individual consultant |  | NSDS Basket Fund | 18th June 2011 | 21th June 2011 | Only one consultant submitted his CV and upon evaluation of his application; NISR Management Committee after being advised by Internal Tender Committee and after considering that there is no interest to re-advertise, it has taken a decision to put this assignment in the ToRs of an other bid Consultancy service to be undertaken by the Institute | 24 months | 25% | CANCELLED |
|  |  | Total amount of tenders awarded/ July 2012 |  |  |  |  |  |  |  | Rwf 13,631,000012 |  |  |  |
|  |  | Total amount cumulative (In Rwf) from July 2012 to the end of August 2012 |  |  |  |  |  |  |  | Rwf 27,791,000 |  |  |  |
|  |  | Total amount of tenders awarded/ September 2012 |  |  |  |  |  |  |  | 14,160,000 |  |  |  |
|  |  | Total amount cumulative at the end of October 2012 (In Rwf) |  |  |  |  |  |  |  | Rwf 27,791,000 |  |  |  |
| 6 | RfP NO 103Pro/S/2012/MIS/NSDS BF | Tenders awarded in November 2012- Provide Technical advice and assistance in improving National Accounts and other key economic statistics | November 2012 to November 2013 | Execut i on | National open tender/CQBS | NCB | NSDS Basket Fund | 03rd July 2012 | 23rd November 2012 | 149,725,782 Rwf | 12 months | 20% | - |
|  |  | Total amount cumulative at the end of November 2012 (In Rwf) |  |  |  |  |  |  |  | 177,516,782 Rwf |  |  |  |

Done at Kigali, on 14/12/2012

Prepared by:                                                                                                     Approved by:

Alphonse SHUMBUSHO                                                                                     Odette MBABAZI

Procurement Officer/NISR                                                                          Deputy Director General of Corporate Services