REPUBLIC OF RWANDA

NATIONAL INSTITUTE OF

STATISTICS OF RWANDA

E-mail :  info@statistics.gov.rw

RAPPORT SUR LES AVENANTS & PENALITES DE RETARD/REPORT ON THE CONTRACT AMENDMENT.

Name of the procuring entity:    National Institute of Statistics of Rwanda (NISR)

Covered Financial year          :    From 31st July 2012 to 30th June 2013

Monthly progress report        :    January 2013

Rapport sur les avenants de contrat/ report on contract amendment

| Nº | Title of the tender | Attributaire/ Successful bidder | Source of funds | Montant de l’avenant attribué s’il y a en eu/Amendment if applicable (In Rwf) | Montant initial du marché/Total amount of the initial tender (In Rwf) | Motif de l’avenant/Reasons for amendments or Justifiable reasons | Montant de penalité de retards s’il y a en eu/Penalties relating to delays in the execution if applicable. |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Total amount of tenders awarded for additional goods not exceed 20% of the initial tender /July 2012: Contract to the value of additional goods not exceeding 20% of the initial tender value according to the article no56 of the Law on Public Procurement no 12/2007 of 27/03/2007 and Ministerial Order no 001/08/10/MIN of 15/01/2008 establishing regulations on Public Procurement. Title of new tender: ‘’SUPPLY SIM CARDS FOR 4,358 BENEFICIARIES OF THE SERVICE’’ CLOSER USER GROUP COMMUNICATION FEES’’ AND ACTIVATION OF SHORT-CODE NO4321 FOR A PERIOD OF ONE (1) MONTH FROM 2ND AUGUST TO 4TH SEPTEMBER 2012’’. Title of the initial tender: “CLOSER USER GROUP COMMUNICATION FEES FOR THE UPCOMING FOURTH 2012 RWANDA POPULATION AND HOUSING CENSUS” | TIGO RWANDA LTD MUHIMA TIGO TOWER P.O BOX 6979 KIGALI – RWANDA | UNFPA Budget | Rwf 2,796,900 The total amount of the contract amendment not exceeding 20% is equivalent to Rwf 2,796,900. This amount includes VAT of 18% and other local taxes. | Rwf 17,192,310 The total amount of the initial tender awarded to TIGO Rwanda was equivalent to (Rwf 17,192,310). This is a total price of bid submitted includes all local taxes and VAT of 18%. | During the reception of census materials in different training centers, the all district census coordinators discovered a shortage of SIM Cards due to the 2uestionnaire2n of team supervisor’s special group which was not reported by district census coordinators. | No penalties applicable to this contract amendment. |
|  | Tenders awarded for additional goods not exceeding 20% of the initial tender / July 2012: | - |  | Rwf 2,796,900 | - | - | - |
| 2 | Tenders awarded for additional goods not exceed 20% of the initial tender /August2012: Contract to the value of additional goods not exceeding 20% of the initial tender value according to the article no56 of the Law on Public Procurement no 12/2007 of 27/03/2007 and Ministerial Order no 001/08/10/MIN of 15/01/2008 establishing regulations on Public Procurement. Title of new tender: ‘’SUPPLY OF ADDITIONAL 120 SIM CARDS FOR BENEFICIARIES OF THE SERVICE’’ CLOSER USER GROUP COMMUNICATION FEES’’ AND ACTIVATION OF SHORT-CODE NO4321 FOR A PERIOD OF ONE (1) MONTH FROM 2ND AUGUST TO 4TH SEPTEMBER 2012’’. Title of the initial tender: “CLOSER USER GROUP COMMUNICATION FEES FOR THE UPCOMING FOURTH 2012 RWANDA POPULATION AND HOUSING CENSUS” | TIGO RWANDA LTD MUHIMA TIGO TOWER P.O BOX 6979 KIGALI – RWANDA | UNFPA Budget | Rwf 541,800 The total amount of the contract amendment not exceeding 20% is equivalent to Rwf 541,800. This amount includes VAT of 18% and other local taxes. | Rwf 17,192,310 The total amount of the initial tender awarded to TIGO Rwanda was equivalent to (Rwf 17,192,310). This is a total price of bid submitted includes all local taxes and VAT of 18%. | During the reception of census materials in different training centers, the all district census coordinators discovered a shortage of SIM Cards due to the 3uestionnaire3n of team supervisor’s special group which was not reported by district census coordinators. | No penalties applicable to this contract amendment. |
| 3 | Title of new tender: ‘’ Packaging of 1300 metallic shelves in warehouse’’. Title of the initial tender: “Supply and installation of furniture for 2012 RPHC” | SOCOMAT LTD 0788303630 POBOX3994 KIGALI-RDA | NSDS Basket Fund | Rwf 672,600 | Rwf 186,686,030 | This amendment was helping NISR to receive the 4uestionnaire from field operation. | No penalties applicable. |
| 4 | Title of new tender: ‘’ Wooden tray to be used in 2012 RPHC data entry’’. Title of the initial tender: “Supply and installation of furniture for 2012 RPHC” | SOCOMAT LTD 0788303630 POBOX3994 KIGALI-RDA | NSDS Basket Fund | Rwf 2,950,000 | Rwf 186,686,030 | This amendment was helping NISR to receive the 4uestionnaire from field operation during the data entry operators. | No penalties applicable. |
|  | Additional goods awarded in August 2012 | - | - | Rwf 4,164,400 | - | - | - |
| 5 | Tenders awarded for additional goods not exceed 20% of the initial tender September 2012- Title of new tender: ‘’ Contract amendment for cleaning, housekeeping, garden flowers services for NISR” Title of the initial tender: “cleaning, housekeeping, garden flowers services for NISR” | TOP CLEANERS LTD | ORDINARY BUDGET | RWF 180,000/ Month to be added on their initial monthly rate of 926,300 Rwf. The initial contract is from 1st June 2012 to 01st June 2013. This amendment contract amount will last for 10 months equivalent to 180,000Rwf/month*10mothns=1,800,000 Rwf | Rwf 11,115,600 | On the previous contract was added twelve (12) new offices and two (2) toilets (former OGMR Office given back to NISR), and Two (2) Halls and one (1) toilet hired by NISR in Manumetal for storage | No penalties applicable |
| 6 | Title of new tender: ‘’ Hiring of 98 motorcycles to be used in the listing of the Post Enumeration Survey (PES-2012) for 3 days 19-21 September 2012 for NISR” Title of the initial tender: “hiring 451 motorcycles in facilitating transport of four hundred fifty one (451) sector’s supervisors during 2012 population and housing census data collection.” | FEDERATION RWANDAISE DES CONDUCTEURS DE TAXI MOTO (FERWACOTAMO) | NSDS Basket Fund | Rwf 5,724,180 | Rwf 193,181,340 | The quality of the housing and population census is vital including reliability and building trust in the work of statistics in Rwanda. | No penalties applicable |
|  | Tenders awarded for additional goods not exceed 20% of the initial tender October 2012 No additional goods tenders not exceed 20% of the initial tenders were awarded in month of October 2012 | - | - | - | - | - | - |
|  | Additional goods tenders added in October 2012 |  |  | Rwf 0 |  |  |  |
| 7 | Tenders awarded for additional goods not exceed 20% of the initial tender November 2012- Title of new tender: “ Four additional unarmed security guards : 2 per day 2 per night;” Title of the initial tender: “Provision of security guards service to NISR” | INTERSEC SECURITY COMPANY | GoR | 2,596,000 Rwf | 18,124,800 Rwf | The Former OGMR offices were handed over to NISR, this was due to increase of the previous covered space | No penalties applicable |
| 8 | Title of new tender: “ Editing andrecording of 4,000 CDs/DVDs used for different NISR Publications;” Title of the initial tender: “Editing and designing of all NISR publications to enhance NISR corporate image for 2 years”” | Great Lakes Communications & Media Centre | NSDS BF | 4,720,000 Rwf | 127,440,000 Rwf | Dissemination purposes | - |
|  | Additional goods tenders added in November 2012 |  |  | 7,316,000 Rwf |  |  |  |
|  | Total amount cumulative at the end of November 2012(In Rwf) for financial year/July 2012 to the end of June 2013 | - | - | Rwf 21,801,480 | - | - | - |
|  | Additional goods tenders added in December 2012 No additional goods tenders not exceed 20% of the initial tenders were awarded in month of December 2012 | - | - |  | - | - | - |
|  | Total amount cumulative at the end of December 2012(In Rwf) for financial year/July 2012 to the end of June 2013 | - | - | Rwf 21,801,480 | - | - | - |
|  | Additional goods tenders added in January 2013 No additional goods tenders not exceed 20% of the initial tenders were awarded in month of January 2013 | - | - |  | - | - | - |
|  | Total amount cumulative at the end of January 2013 (In Rwf) for financial year/July 2012 to the end of June 2013 | - | - | Rwf 21,801,480 |  |  |  |

Done at Kigali, 13/02/2013

Prepared by:                                                                                                       Approved by:

Alphonse SHUMBUSHO						Odette MBABAZI

Procurement Officer/NISR                                                                           Deputy Director General of Corporate Services