REPUBLIC OF RWANDA

NATIONAL INSTITUTE OF

STATISTICS OF RWANDA

E-mail :  info@statistics.gov.rw

RAPPORT SUR LES AVENANTS & PENALITES DE RETARD/REPORT ON THE CONTRACT AMENDMENT.

Name of the procuring entity:    National Institute of Statistics of Rwanda (NISR)

Covered Financial year          :    From 31st July 2012 to 30th June 2013

Monthly progress report        :   July 2012

| Nº | Title of the tender | Attributaire/ Successful bidder | Source of funds | Montant de l’avenant attribué s’il y a en eu/Amendment if applicable (In Rwf) | Montant initial du marché/Total amount of the initial tender (In Rwf) | Motif de l’avenant/Reasons for amendments or Justifiable reasons | Montant de penalité de retards s’il y a en eu/Penalties relating to delays in the execution if applicable. |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Total amount of tenders awarded for additional goods not exceed 20% of the initial tender /July 2012: Contract to the value of additional goods not exceeding 20% of the initial tender value according to the article no56 of the Law on Public Procurement no 12/2007 of 27/03/2007 and Ministerial Order no 001/08/10/MIN of 15/01/2008 establishing regulations on Public Procurement. Title of new tender: ‘’SUPPLY SIM CARDS FOR 4,358 BENEFICIARIES OF THE SERVICE’’ CLOSER USER GROUP COMMUNICATION FEES’’ AND ACTIVATION OF SHORT-CODE NO4321 FOR A PERIOD OF ONE (1) MONTH FROM 2ND AUGUST TO 4TH SEPTEMBER 2012’’. Title of the initial tender: “CLOSER USER GROUP COMMUNICATION FEES FOR THE UPCOMING FOURTH 2012 RWANDA POPULATION AND HOUSING CENSUS” | TIGO RWANDA LTD MUHIMA TIGO TOWER P.O BOX 6979 KIGALI - RWANDA | UNFPA Budget | Rwf 2,796,900 The total amount of the contract amendment not exceeding 20% is equivalent to Rwf 2,796,900. This amount includes VAT of 18% and other local taxes. | Rwf 17,192,310 The total amount of the initial tender awarded to TIGO Rwanda was equivalent to (Rwf 17,192,310). This is a total price of bid submitted includes all local taxes and VAT of 18%. | During the reception of census materials in different training centers, the all district census coordinators discovered a shortage of SIM Cards due to the underestimation of team supervisor’s special group which was not reported by district census coordinators. | No penalties applicable to this contract amendment. |
|  | Tenders awarded for additional goods not exceeding 20% of the initial tender / July 2012: | - |  | 2,796,900 | - | - | - |
|  | Total amount cumulative (In Rwf) for financial year/July 2012 to the end of June 2013 | - | - | 2,796,900 | - | - | - |

Done at Kigali, 14/08/2012

Prepared by:                                                                                                       Approved by:

Eric BUGINGO                                                                                                    Odette MBABAZI

Procurement Officer/NISR                                                                           Deputy Director General of Corporate Services