## FY 2011-12
NISR GENERAL PROCUREMENT PLAN FOR THE NATIONAL INSTITUTE OF STATISTICS OF RWANDA/ FROM JULY 2011 TO JUNE 2012
N° | Title of Tender | Type of supply | Estimated cost(RWF) | Source of funds | Tendering method | Prequalif.(Yes/No) | Prior study(Yes/No) | Local prefer.(Yes/No) | No objection/DAO | RPPA and Financing | Publication | No objection/Evaluation report | Contract Management
July, 2011
1 | Acquisition of new IT equpments for the procurement team (printer, scanner, laptop, heavy duty safe, filing cabinets) | Goods | 9000000 | B.F. | NOCBM | No | No | No | No | No | July, 2011 | No | 2011-10-09
2 | Design and Printing questionnaires used in data collection /one year contract period | Goods | 80000000 | All budgets | NOCBM | No | No | No | No | No | July, 2011 | No | 2011-10-09
3 | Design and Printing all types of books used in dissemination of results /one year contract period | Goods | 30000000 | All budgets | NOCBM | No | No | No | No | No | July, 2011 | No | 2011-10-09
4 | Acquisition of 60 rain coats for field staff of pilot census | Goods | 1000000 | UNFPA | R.F.Q./Shopping | No | No | No | No | No | July, 2011 | No | 2011-08-10
5 | Support EICV III, 2010 Team to hiring boat owner to facilitate the transportation of enumerators in Island Nkombo in Lake Kivu/Rusizi District | Goods | 475000 | UNFPA | R.F.Q./Shopping | No | No | No | No | No | July, 2011 | No | 2011-08-10
6 | Acquisition of 55 covers of GPS/45 tremble and 10 Juno | Goods | 1500000 | UNFPA | R.T.M. | No | No | No | No | No | July, 2011 | No | 2011-08-27
7 | Acquisition of 150 torches rechageables for field staff of pilot census | Goods | 2700000 | UNFPA | R.T.M. | No | No | No | No | No | July, 2011 | No | 2011-08-27
8 | Acquisition of 40 snake bit kit for field staff of pilot census | Goods | 1200000 | UNFPA | R.T.M. | No | No | No | No | No | July, 2011 | No | 2011-08-27
9 | Procurement of 200 batteries and other ICT consummables | Goods | 31008040 | B.F. | NOCBM | No | No | No | No | No | July, 2011 | No | 2011-10-09
10 | Provision of office supplies and consumables,stationeries | Goods | 21250000 | UNFPA | NOCBM | No | No | No | No | No | July, 2011 | No | 2011-10-09
11 | Design and production of NISR orientation sign | Goods | 1000000 | UNFPA | NOCBM | No | No | No | No | No | July, 2011 | No | 2011-10-09
12 | Supply of 100 tyres for new 20 toyota pick-ups 4x4 | Goods | 16800000 | UNFPA | NOCBM | No | No | No | No | No | July, 2011 | No | 2011-10-09
13 | Supply of materials for field staff of pilot census/new 36 cartographers | Goods | 7137500 | UNFPA | NOCBM | No | No | No | No | No | July, 2011 | No | 2011-10-09
14 | Supply of materials for field staff of pilot census/Data collection of pilot census | Goods | 6884000 | UNFPA | NOCBM | No | No | No | No | No | July, 2011 | No | 2011-10-09
15 | Acquisition of batteries for field staff cartographers/census mapping | Goods | 1440000 | UNFPA | NOCBM | No | No | No | No | No | July, 2011 | No | 2011-10-09
16 | Supply of 20 tyres for 5 Vehicles deployed in the field in volcanic areas at North and West Provinces near Nyungwe Forest whre the roads are in very poor conditions. | Goods | 3186000 | UNFPA | NOCBM | No | No | No | No | No | July, 2011 | No | 2011-10-09
17 | Design and production of NISR orientation sign | Goods | 1000000 | UNFPA | R.F.Q./Shopping | No | No | No | No | No | July, 2011 | No | 2011-08-10
18 | Acquisition of 8 shelves of census unit | Goods | 5440000 | UNFPA | NOCBM | No | No | No | No | No | July, 2011 | No | 2011-10-09
19 | Procurement of modems for laptops used by all Directors, Coordinators and Supervisors on the field operations | Goods | 587200 | B.F. | R.F.Q./Shopping | No | No | No | No | No | July, 2011 | No | 2011-08-10
20 | Insurance for old 23 NISR vehicles used in data collection | Goods | 2500000 | UNFPA | R.T.M. | No | No | No | No | No | July, 2011 | No | 2011-08-27
21 | Collective insurance for new cartographers of pilot census | Goods | 1500000 | UNFPA | R.T.M. | No | No | No | No | No | July, 2011 | No | 2011-08-27
22 | Facilities for hosting 2 workshops on trade statistics (Aug and Nov 2011) | Service | 3000000 | B.F. | NOCBM | No | No | No | No | No | July, 2011 | No | 2011-10-09
23 | Acquisition of laptops, modems and printers for LCD-DM project | Goods | 2000000 | LCD-DM | NOCBM | No | No | No | No | No | July, 2011 | No | 2011-10-09
24 | Recruitment of international expert on trade statistics | Service | 11000000 | B.F. | NOCBM | No | No | No | No | No | July, 2011 | No | 2011-10-09
25 | Acquisition of CPI survey equipments and field kits | Goods | 6700000 | AFDB | NOCBM | No | No | No | No | No | July, 2011 | No | 2011-10-09
26 | Facilities for quarterly National Accounts workshops (3-years) | Service | 20000000 | AFDB | NOCBM | No | No | No | No | No | July, 2011 | No | 2011-10-09
27 | Recruitment of International Consultant for construction and civil engineering for ICP | Service | 11000000 | AFDB | NOCBM | No | No | No | No | No | July, 2011 | No | 2011-10-09
28 | Recruitment of International Consultant for GDP estimates breakdown | Service | 11000000 | AFDB | NOCBM | No | No | No | No | No | July, 2011 | No | 2011-10-09
29 | Recruitment of International Consultant for NGO study | Service | 11000000 | AFDB | NOCBM | No | No | No | No | No | July, 2011 | No | 2011-10-09
30 | Recruitment of International Consultant for capital goods industry study | Service | 11000000 | AFDB | NOCBM | No | No | No | No | No | July, 2011 | No | 2011-10-09
31 | Facilities for hosting provincial workshops on administrative statistics | Service | 3000000 | LCD-DM | NOCBM | No | No | No | No | No | July, 2011 | No | 2011-10-09
32 | Facilities for dissemination workshops of vital statistics | Service | 3000000 | UNFPA | NOCBM | No | No | No | No | No | July, 2011 | No | 2011-10-09
33 | Recruitment of international consultant for data processing and analysis of Manpower survey | Service | 18000000 | M.S.P. | NOCBM | No | No | No | No | No | July, 2011 | No | 2011-10-09
34 | Recruitment of a company to conduct security service at the National Institute of Statistics of Rwanda | Service | 12744000 | O.B. | NOCBM | No | No | No | No | No | July, 2011 | No | 2011-10-06
35 | Training of new 56 cartographers of pilot census | Service | 6764000 | UNFPA | Contract signed. | - | No | No | No | No | July, 2011 | No | -
36 | Ensure effective induction process for new staff | Service | 1000000 | O.B. | R.F.Q./Shopping | No | No | No | No | No | July, 2011 | No | 2011-08-10
37 | Sourcing of restaurant based in Kigali City for accomodation service during the conferences, meetings organized at NISR | Service | 5760000 | O.B. | NOCBM | No | No | No | No | No | July, 2011 | No | 2011-10-06
38 | Re-advertisement tender for maintenance of IT equipments | Service | 8500000 | O.B. | NOCBM | No | No | No | No | No | July, 2011 | No | 2011-10-09
39 | Repairing and maintenance of NISR vehicles/Contract for one year period | Service | 30000000 | B.F. | NOCBM | No | No | No | No | No | July, 2011 | No | 2011-10-09
40 | Hiring a company which must provide a High Spatial Resolution Image for Kigali City during the 2012 RPHC | Service | 25000000 | UNFPA | NOCBM | Yes | No | No | No | No | July, 2011 | No | 2011-10-09
41 | Update NISR Asset register and engraving new incoming assets | Service | 7000000 | O.B. | NOCBM | No | No | No | No | No | July, 2011 | No | 2011-10-09
42 | International consultancy for Agricultural Crop Production Statistics/Contract for one year period | Service | 150000000 | B.F. | IOCBM | Yes | No | No | No | No | July, 2011 | No | 2011-10-24
43 | Recruitment of an international consultant who will support the implementation of Manpower Survey Project | Service | 13500000 | M.S.P. | IOCBM | Yes | No | No | No | No | July, 2011 | No | 2011-10-24
| TOTAL AMOUNT/ July, 2011 |  | 596575740
August, 2011
1 | Design and printing of ICP Catalogues for all price collectors | Goods | 2637000 | B.F. | NOCBM | No | No | No | No | No | Aug, 2011 | No | 2011-10-13
2 | Acquisition of some materials for CPI Price collectors | Goods | 1500000 | B.F. | NOCBM | No | No | No | No | No | Aug, 2011 | No | 2011-10-15
3 | Acquisition of 150 bags for enumerators of EICV III, 2010 | Goods | 1200000 | B.F. | NOCBM | No | No | No | No | No | Aug, 2011 | No | 2011-10-15
4 | Production and dissemination of 2011 Statistical Year Book/Data collection+ printing | Goods | 7450000 | B.F. | AAOON | No | No | No | No | No | Aug, 2011 | No | 2010-11-01
5 | Design and printing of Rwanda facts and figures leaflets | Goods | 800000 | B.F. | R.F.Q./Shopping | No | No | No | No | No | Aug, 2011 | No | 2011-08-16
6 | Contributing to EDPRS progress reports, MDG reports, EAC facts and fugures/Meetings, workshops and trainings | Goods | 1100000 | B.F. | R.T.M. | No | No | No | No | No | Aug, 2011 | No | 2011-09-03
7 | Delivery of 80 new PCs and 802 small UPSs | Goods | 61520000 | UNDP | Rest payment | - | No | No | No | No | Aug, 2011 | No | -
8 | Printing of 300 copies of Visa Instruction Manuals | Goods | 750000 | B.F. | R.F.Q./Shopping | No | No | No | No | No | Aug, 2011 | No | 2011-08-16
9 | Printing of 300 copies of Rwanda facts and figures. | Goods | 750000 | B.F. | R.F.Q./Shopping | No | No | No | No | No | Aug, 2011 | No | 2011-08-16
10 | Design and printing of 500 copies of counting the people of Rwanda /Census unit | Goods | 965000 | B.F. | R.F.Q./Shopping | No | No | No | No | No | Aug, 2011 | No | 2011-08-16
11 | Design and Printing of questionnaires A and B to be used on the field by EICV III, 2010 enumerators | Goods | 4908000 | B.F. | NOCBM | No | No | No | No | No | Aug, 2011 | No | 2011-10-15
12 | Acquisition of 100 computers and 5 laptops for Local Capacity Development Project in Data Management | Goods | 82000000 | LCD-DM | NOCBM | No | No | No | No | No | Aug, 2011 | No | 2011-10-23
13 | Outsource services of a company that can help to design NISR logo | Service | 1500000 | O.B. | NOCBM | No | No | No | No | No | Aug, 2011 | No | 2011-10-15
14 | Upgrade of NISR and former CEPEX Network for a period of one year | Service | 40000000 | B.F. | Rest contract | - | No | No | No | No | Aug, 2011 | No | -
| TOTAL AMOUNT/ August, 2011 |  | 207080000
September, 2011
1 | CPI Evaluation and orientation workshop arranged | Service | 10060000 | B.F. | NOCBM | No | No | No | No | No | Sept, 2011 | No | 2011-11-06
2 | Workshop on crop work in progress model with NISR staff involved in data collection of CPI and key stakeholders | Service | 8560000 | B.F. | NOCBM | No | No | No | No | No | Sept, 2011 | No | 2011-11-10
3 | Supply of materials and equipments for cartography field (computers, laptops, GPS, office equip., etc) |  | 165911900 | UNFPA | NOCBM | No | No | No | No | No | Sept, 2011 | No | 2011-11-13
4 | Workshop an industrial statistics users needs assessment/Road map designed/materials of workshop | Service | 450000 | B.F. | R.F.Q./Shopping | No | No | No | No | No | Sept, 2011 | No | 2011-09-07
5 | DevInfo training for NISR Staff and key stakeholders | Service | 5570000 | ICP funds | NOCBM | No | No | No | No | No | Sept, 2011 | No | 2011-11-17
6 | Revamping of NISR updating Website | Service | 5900000 | B.F. | Rest payment | - | No | No | No | No | Sept, 2011 | No | -
7 | Subcontracting a professional company to edit all our publications including designing their layout to enhance NISR Corporate Services | Service | 3200000 | B.F. | EOI | Yes | No | No | No | No | Sept, 2011 | No | 2011-11-20
8 | Workshop related to the preparation of 2nd quarter work plan fro FY 2011/2012 and reporting on 1st quarter work plan/July to September 2011 | Service | 450000 | B.F. | R.F.Q./Shopping | No | No | No | No | No | Sept, 2011 | No | 2011-09-12
9 | Enhance NSS Coordination framework seminar finalized and the cabinet paper drafted/meetings, workshops and seminars organized at all sectors level | Service | 18600000 | B.F. | NOCBM | No | No | No | No | No | Sept, 2011 | No | 2011-11-24
| TOTAL AMOUNT/ Septemeber 2011 |  | 218701900
October, 2012
1 | Supply of materials for field staff /Data collection of pilot census (batteries, pencils, rain coats, etc) | Goods | 15461500 | UNFPA | NOCBM | No | No | No | No | No | Oct, 2011 | No | 2011-11-24
2 | Supply of materials for data exploitation( coding, data entry, tabulation, etc)/meetings, conferences | Goods | 5461500 | UNFPA | NOCBM | No | No | No | No | No | Oct, 2011 | No | 2011-11-27
3 | Supply of materials for data analysis and evaluation completed/organization of meeting with stakeholders | Goods | 4461500 | UNFPA | NOCBM | No | No | No | No | No | Oct, 2011 | No | 2011-11-27
4 | Refurbishment on NISR premises/Hiring a consulting firm for the rehabilitation of former MINIPLAN building | Service | 25000000 | O.B. | NOCBM | No | No | No | No | No | Oct, 2011 | No | 2011-11-27
| TOTAL AMOUNT/ October 2011 |  | 50384500
November, 2012
1 | Census enumeration sensitisation tools (T-shirts, folders, charts, posters, pullups, etc) printed | Goods | 18000000 | UNFPA | NOCBM | No | No | No | No | No | Nov, 2011 | No | 2011-12-08
2 | Facilities for Census-related trainings, short courses, seminars etc (3 year contract) | Service | 213000000 | O.B. | NOCBM | No | No | No | No | No | Nov, 2012 | Yes | 2011-12-11
| TOTAL AMOUNT/ November 2011 |  | 231000000
December, 2012
1 | Printing Census brochures, manuals, leaflets and other documents | Goods | 11000000 | B.F. | NOCBM | No | No | No | No | No | Dec, 2011 | No | 2011-12-11
2 | Insurance for new 20 vehicles pick-ups toyota 4x4 used in data collection | Goods | 2500000 | UNFPA | NOCBM | No | No | No | No | No | Dec, 2011 | No | 2012-01-26
3 | Supply of consummables for NISR Cafeteria for one year contract period | Goods | 6500000 | UNFPA | NOCBM | No | No | No | No | No | Dec, 2011 | No | 2012-01-26
4 | Recruitment of international Consultant for CPI | Service | 10200000 | B.F. | NOCBM | No | No | No | No | No | Dec, 2011 | No | 2011-12-18
5 | Facilities for CPI workshops (Feb 2012, Jun 2012, Nov 2012, Mar 2013, Jun 2013, Nov 2013) | Service | 37500000 | B.F. | NOCBM | No | No | No | No | No | Dec, 2011 | No | 2011-12-22
6 | Refurbishment on NISR premises/Hiring a consulting firm for monitoring of the rehabilitation/former MINIPLAN building | Service | 25000000 | O.B. | NOCBM | No | No | No | No | No | Dec, 2011 | No | 2012-01-01
7 | Upgrading existing statistical software (SPSS,STAT) to ensure compatibility with new operating systems | Service | 52000000 | B.F. | NOCBM | No | No | No | No | No | Dec, 2011 | No | 2012-01-01
| TOTAL AMOUNT/ December 2011 |  | 144700000
January, 2012
1 | Procurement of some equipments, materials of census, tools designed and printed of sensitisation compaign conducted/2012 RPHC | Goods | 3600000 | UNFPA | NOCBM | No | No | No | No | No | Jan, 2012 | No | 2012-03-22
2 | One year contract/Supply of office cartridges/toners, drums, etc for all printers and photocopiers of NISR | Goods | one year contract | All budgets | NOCBM | No | No | No | No | No | Jan, 2012 | No | 2012-04-01
3 | One year contract/Supply of toners, drums, fuser film, etc for 5 digital photocopiers-MFP | Goods | 6828886 | O.B. | NOCBM | No | No | No | No | No | Jan, 2012 | No | 2012-04-01
4 | Supply of materials and equipments to be used in sensitization and publicity of 2012 RPHC | Goods | 15422500 | UNFPA | NOCBM | No | No | No | No | No | Jan, 2012 | No | 2012-03-22
5 | Design and printing of documents to be used in sensitization and publicity of 2012 RPHC | Goods | 11375000 | UNFPA | NOCBM | No | No | No | No | No | Jan, 2012 | No | 2012-03-22
6 | Printing and binding of statistical year book | Goods | 9000000 | B.F. | NOCBM | No | No | No | No | No | Jan, 2012 | No | 2012-03-25
7 | Recruitment of international consultant for producing manuals on statistical classification | Service | 50000000 | B.F. | NOCBM | No | No | No | No | No | Jan, 2012 | No | 2012-04-01
8 | Contract for providing one year service of maintaining NISR building including 25 air conditioners | Service | 7500000 | O.B. | NOCBM | No | No | No | No | No | Jan, 2012 | No | 2012-03-22
9 | Software for Logistics management purchased and maintained | Service | 30000000 | O.B. | NOCBM | No | No | No | No | No | Jan, 2012 | No | 2012-03-22
| TOTAL AMOUNT/ January 2012 |  | 133726386
February, 2012
1 | Procurement of some equipments, materials of census, tools designed and printed of sensitisation compaign conducted/2012 RPHC | Goods | 3600000 | B..F. | NOCBM | No | No | No | No | No | Feb, 2012 | No | 2012-04-12
2 | Conception, printing and installation of banners, pull-ups, etc/one year contract | Goods | one year contract | B.F. | NOCBM | No | No | No | No | No | Feb, 2012 | No | 2012-04-26
3 | Printing and binding of DHS3 results by all Districts | Goods | 14000000 | O.B. | NOCBM | No | No | No | No | No | Feb, 2012 | No | 2012-04-30
4 | Supply of office stationary for one year contract period | Goods | one year contract | O.B. | NOCBM | No | No | No | No | No | Feb, 2012 | No | 2012-04-30
5 | EICV3 data analysis workshop facilities | Service | 8000000 | B.F. | NOCBM | No | No | No | No | No | Feb, 2012 | No | 2012-04-19
6 | Recruitment of international Consultant for PPI (USBLS) | Service | 10200000 | B.F. | NOCBM | No | No | No | No | No | Feb, 2012 | No | 2012-04-26
7 | Refurbishment on NISR premises | Works | 540000000 | O.B. | NOCBM | No | No | No | No | No | Feb, 2012 | No | 2012-05-05
| TOTAL AMOUNT/ February2012 |  | 575800000
March, 2012
1 | Final version of Census enumeration questionnaires and manuals printed | Goods | 340000000 | B.F. | NOCBM | No | Yes | Yes | Yes | Yes | March, 2012 | Yes | 2012-05-10
2 | Design and printing of draft report on poverty statistics produced | Goods | 6000000 | B.F. | NOCBM | No | Yes | Yes | Yes | Yes | March, 2012 | Yes | 2012-05-24
3 | Procurement of some equipments, materials of census, tools designed and printed of sensitisation compaign conducted/2012 RPHC | Goods | 4248000 | B.F. | NOCBM | No | Yes | Yes | Yes | Yes | March, 2012 | Yes | 2012-05-31
4 | Supply of fuel and gasoline for all NISR vehicles used in the field during the data collection | Goods | one year contract | All budgets | NOCBM | No | Yes | Yes | Yes | Yes | March, 2012 | Yes | 2012-05-31
5 | Printing of business cards, electronic cards, badges, etc for NISR staff | Goods | 1500000 | O.B. | NOCBM | No | Yes | Yes | Yes | Yes | March, 2012 | Yes | 2012-05-31
6 | Recruitment of a consultancy firm to produce a strategy for develping a modern statistical information centre | Service | 20000000 | B.F. | NOCBM | No | Yes | Yes | Yes | Yes | March, 2012 | Yes | 2012-05-17
7 | Hosting and Updating NISR website | Service | 7000000 | B.F. | NOCBM | No | Yes | Yes | Yes | Yes | March, 2012 | Yes | 2012-05-31
8 | Sport activities subscription for the staff of National Institute of Statistics of Rwanda | Service | 7500000 | O.B. | NOCBM | No | Yes | Yes | Yes | Yes | March, 2012 | Yes | 2012-05-31
9 | Cleaning service for one year contract period | Service | 14000000 | O.B. | NOCBM | No | Yes | Yes | Yes | Yes | March, 2012 | Yes | 2012-05-31
| TOTAL AMOUNT/ March 2012 |  | 400248000
April, 2012
1 | Design and printing of draft national report of EICV III, 2010 produced | Goods | 3500000 | B.F. | NOCBM | No | No | No | No | No | April, 2012 | No | 2012-06-21
2 | Design and printing a party of final version of questionnaires and manuals of 2012 RPHC | Goods | 100000000 | B.F. | NOCBM | No | No | No | No | No | April, 2012 | No | 2012-06-24
3 | Procurement of some equipments, materials of census, tools designed and printed of sensitisation compaign conducted/2012 RPHC | Goods | 5600000 | B.F. | NOCBM | No | No | No | No | No | April, 2012 | No | 2012-07-05
4 | Decentralised dissemination of DHS III, 2010 results in all Districts(printing books, meetings,etc) | Goods | 10000000 | UNICEF | NOCBM | No | No | No | No | No | April, 2012 | No | 2012-07-05
5 | Facilities for training and validation workshops for Rebasing GDP estimates | Service | 1500000 | B.F. | NOCBM | No | No | No | No | No | April, 2012 | No | 2012-06-14
6 | Start the procurement for hiring hotels for accomodation services in all provinces/One year contract | Service | one year contract | All budgets | NOCBM | No | No | No | No | No | April, 2012 | No | 2012-06-14
7 | Hiring hotel for test of the staff to be recruited of 2012 RPHC | Service | 9089250 | B.F. | NOCBM | No | No | No | No | No | April, 2012 | No | 2012-07-01
| TOTAL AMOUNT/ April 2012 |  | 129689250
May, 2012
1 | Post-Enumeration Survey documents printed | Goods | 5600000 | O.B. | NOCBM | No | No | No | No | No | May, 2012 | No | 2012-07-12
2 | Supply symantec endpoint protection antivirus for one year subscription to protect severs with 250 licenses | Goods | 3000000 | B.F. | NOCBM | No | No | No | No | No | May, 2012 | No | 2012-07-12
3 | Procurement of some equipments, materials of census, tools designed and printed of sensitisation compaign conducted/2012 RPHC | Goods | 3600000 | B.F. | NOCBM | No | No | No | No | No | May, 2012 | No | 2012-07-15
4 | Procurement of materials and equipments of enumerators, supervisors of 2012 RPHC/August 2012 | Goods | 250777000 | B.F. | NOCBM | No | No | No | No | No | May, 2012 | No | 2012-07-29
| TOTAL AMOUNT/ May 2012 |  | 262977000
June, 2012
1 | Design and printing of thematic reports of EICV III, 2010 produced | Goods | 2500000 | B.F. | NOCBM | No | No | No | No | No | June, 2012 | No | 2012-07-22
2 | Design and printing final version of questionnaires(2,500,000) and manuals(19,000) of 2012 RPHC | Goods | 50000000 | B.F. | NOCBM | No | No | No | No | No | June, 2012 | No | 2012-07-26
3 | Design and printing EA booklets(15,000) and recapitulation documents of 2012 RPHC | Goods | 9750000 | B.F. | NOCBM | No | No | No | No | No | June, 2012 | No | 2012-07-26
4 | Printing of 19,000 badges of enumerators of 2012 RPHC | Goods | 4940000 | B.F. | NOCBM | No | No | No | No | No | June, 2012 | No | 2012-07-26
5 | Sensitization, Publicity and printing of documents of 2012 RPHC/August 2012 | Goods | 9257300 | UNFPA | NOCBM | No | No | No | No | No | June, 2012 | No | 2012-08-05
6 | Recruitment of local IT expert to update public websites | Service | 6000000 | B.F. | NOCBM | No | No | No | No | No | June, 2012 | No | 2012-08-05
7 | Hiring hotel for accomodation service/field staff recruited and trained of 2012 RPHC | Service | 593089250 | B.F. | NOCBM | No | No | No | No | No | June, 2012 | No | 2012-07-29
8 | Rent of vehicles for enumerators, rent of trucks for filed material transportation and for Team Leaders | Service | 859300000 | B.F. | NOCBM | No | No | No | No | No | June, 2012 | No | 2012-07-29
9 | Recruitment of international consulting firm for improving livestock and poultry statistics forecasting | Service | 21000000 | B.F. | NOCBM | No | No | No | No | No | June, 2012 | No | 2012-08-02
| Total June-2012 |  | 1555836550
| General Total July-2011 up to June-2012 |  | 4506719326
B.F: BASKET FUND
RF: Request for Quotations/Shopping
EOI: Expression Of Interest for services
NOCBM: National Open Competitive Bidding Method
IOCBM: International Open Competitive Bidding Method
RTM : Restricted Tendering Method
QCBS : Quality & Cost Based Selection
SS Or DC: Single Source: Entente Directe ou Marché de Gré à Gré ( Direct Contracting)
OB :Ordinary Budget
R-DHS: Rwanda Demographic Health Survey
NISR : National Institute of Statistics of Rwanda
ICT: Information & Communication Technology
UNFPA: United Nations Population Fund
ICP:International Comparison Program
UNICEF: United Nations Children's Fund
LCD-DM:Local Capacity Development in Data Management Project
UNDP: United Nations Development Program
AfDB:African Development Bank
MSP: Manpower Survey Project
2012RPHC: 2012 Rwanda Population and Housing Census
RPPA: Rwanda Public Procurement Authority
TD: Tender Document
Done at Kigali, on 28th July 2011
| Prepared by: | [8 empty] | Approved by:
Alphonse SHUMBUSHO
Procurement Officer/National Institute of Statistics of Rwanda
| Eric BUGINGO | [8 empty] | Odette MBABAZI
| Procurement Officer/National Institute of Statistics of Rwanda | [8 empty] | Deputy Director General of Corporate Services

## FY 2013-14final
REVISED PROCUREMENT PLAN FOR THE NATIONAL INSTITUTE OF STATISTICS OF RWANDA FOR THE FINANCIAL YEAR STARTING JULY 2013 TO JUNE 2014
N° | Type | Title of Tender | Source of funds | Tendering method | Planned tender document preparation date | Planned publication date | Planned bid opening date | Planned provisional notification date | Planned contract signing date | Recruitment of the supervising firm (Yes/No | Planned contract management start date | Planned contract closure date | Other information: Prior study, need of specialist for TS or TOR and/or contract management, pre-qualification, Local preference, No objection from funding institutions, etc.
July, 2013/Tenders for goods and non consultancy services
1 |  | Providing Hotel Services in Kigali City-Medium Level with at least capacity to host above 200 participants | GOR Budget and other budgets allocated to NISR like NSDS Basket Fund support to NISR | NCB | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | End of July 2015 | This is Framework Contract for a period of 2 years. This tender was awarded in fiscal year 2012-2013 but as it will be a continuation for 2 years, means that this fiscal year 2013-2014, we will need a service from the Successful Bidder. So we prefer to plan in this fiscal year a total amount of Rwf 50,000,000 for a period one year
2 |  | Sourcing of Hotels, Motels, etc to organize conference facilities, accomodation services and other logistics requirements located outside of Kigali City(In all Provinces) | GOR Budget and other budgets allocated to NISR like NSDS Basket Fund support to NISR | NCB | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | End of July 2015 | This is Framework Contract for a period of 2 years. This tender was awarded in fiscal year 2012-2013 but as it will be a continuation for 2 years, means that this fiscal year 2013-2014, we will need a service from the Successful Bidder. So we prefer to plan in this fiscal year a total amount of Rwf 50,000,000 for a period one year
3 |  | Providing VIP Hotel Services for all VIP events such as dissemination of survey results on National level, launching of big researches or surveys, etc for a period of two(2) years | GOR Budget and other budgets allocated to NISR like NSDS Basket Fund support to NISR | NCB | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | End of July 2015 | This is Framework Contract for a period of 2 years. This tender was awarded in fiscal year 2012-2013 but as it will be a continuation for 2 years, means that this fiscal year 2013-2014, we will need a service from the Successful Bidder. So we prefer to plan in this fiscal year a total amount of Rwf 50,000,000 for a period one year
4 |  | Cleaning service for NISR offices for a period of two(2) years | GOR Budget | NCB | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | End of July 2015 | This is Framework Contract for a period of 2 years. This tender was awarded in fiscal year 2012-2013 but as it will be a continuation for 2 years, means that this fiscal year 2013-2014, we will need a service from the Successful Bidder. So we prefer to plan in this fiscal year a total amount of Rwf 1,133,272 per month equal to Rwf 13,599,264 for a period one year
5 |  | Design, Printing and installation of BillBoards, Banners of any size, Pull-ups banners and other related materials and services for 2 years contract | GOR Budget and other budgets allocated to NISR like NSDS Basket Fund support to NISR | NCB | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | End of August 2015 | This is Framework Contract for a period of 2 years. This tender was awarded in fiscal year 2012-2013 but as it will be a continuation for 2 years, means that this fiscal year 2013-2014, we will need a service from the Successful Bidder. So we prefer to plan in this fiscal year a total amount of Rwf 7,000,000 for a period one year
6 |  | Printing of business cards, ID cards, invitation cards, greeting cards, badges, for NISR staff, Visitor's cards, stamps, ink pads for self ink stamps and other types of cards and other related materials and services | GOR Budget and other budgets allocated to NISR like NSDS Basket Fund support to NISR | NCB | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | End of August 2015 | This is Framework Contract for a period of 2 years. This tender was awarded in fiscal year 2012-2013 but as it will be a continuation for 2 years, means that this fiscal year 2013-2014, we will need a service from the Successful Bidder. So we prefer to plan in this fiscal year a total amount of Rwf 1,500,000 for a period one year
7 |  | Supply airtime and other related needs for NISR staff and fieldworkers | GOR Budget and other budgets allocated to NISR like NSDS Basket Fund support to NISR | NCB | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | End of August 2015 | This is Framework Contract for a period of 2 years. This tender was awarded in fiscal year 2012-2013 but as it will be a continuation for 2 years, means that this fiscal year 2013-2014, we will need a service from the Successful Bidder. So we prefer to plan in this fiscal year a total amount of Rwf 24,000,000 for a period one year
8 |  | Supply of 60 GPS devices for National Agricultural Survey 2012-2013 and for EICV4 fieldworkers | NSDS B.F. | NCB | 2013-05-06 | 2013-05-11 | 2013-06-10 | 2013-07-01 | 2013-08-10 | No | 2013-08-20 | 2013-09-19 | GPS to be used by EICV4 Fieldworkers
9 |  | Supply of 217 tires for the vehicles used by National Institute of Statistics of Rwanda. | NSDS B.F. | NCB | 2013-05-06 | 2013-05-11 | 2013-06-10 | 2013-07-01 | 2013-07-22 | No | 2013-07-26 | 2013-08-25 | Tyres to be used by NISR vehicles on EICV4 field operation
|  | Supply of 190 heavy-duty back bags (for EICV4 field workers) immediately and Supply of the same items on regular basis for a period of two(2) years | NSDS B.F. | NCB | 2013-05-16 | 2013-05-26 | 2013-06-25 | 2013-07-25 | 2013-08-26 | No | 2013-08-26 | 2013-09-25 | 190 Bags to be used by EICV4 Fieldworkers and Fr.Contract/2years
10 |  | Supply and installation of symantec antivirus to protect all NISR computers | NSDS B.F. | NCB | 2013-05-24 | 2013-06-03 | 2013-07-03 | 2013-08-02 | 2013-08-22 | No | 2013-08-25 | 2013-09-24 | Antivirus to protect all NISR computers and servers machines
11 |  | Publication of NISR Tenders, Articles, Announcements, etc./National Newspapers | O.B. | NCB | 2013-07-12 | 2013-07-26 | 2013-08-25 | 2013-09-15 | 2013-10-06 | No | 2013-10-10 | 2015-10-10
12 |  | Publication of NISR tenders, articles, announcements, etc./Regional Newspapers | O.B. | NCB | 2013-07-15 | 2013-07-29 | 2013-08-28 | 2013-09-18 | 2013-10-09 | No | 2013-10-13 | 2015-10-13
13 |  | Supply and installation of glass tinted films for NISR Building windows. | GOR Budget | RFQ | 2013-07-16 | 2013-07-19 | 2013-07-23 | 2013-07-25 | 2013-07-27 | No | 2013-08-10 | 2013-08-15
14 |  | Event management and other related services for events organized by NISR | GOR Budget and other budgets allocated to NISR like NSDS Basket Fund support to NISR | NCB | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | End of July 2015 | This is Framework Contract for a period of 2 years. This tender was awarded in fiscal year 2012-2013 but as it will be a continuation for 2 years, means that this fiscal year 2013-2014, we will need a service from the Successful Bidder. So we prefer to plan in this fiscal year a total amount of Rwf 7,500,000 for only a period one year
15 |  | Supply of 14 modems with internet service and internet service for 6 months for the Rwanda Population and Housing Census | NSDS Basket Fund Support to NISR | RTM | 2013-07-01 | 2013-07-05 | 2013-07-19 | 2013-08-09 | 2013-08-16 | No | 2013-08-19 | 2013-08-29 | The expected time for delivery of modems is 29/08/2013 and internet service for 6 months up to the end of March 2014
16 |  | Supply of materials for re-installation of 2 air conditioners in the new server room | GOR Budget | Framework Contract | Planned and award in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | End of August 2013 (31/08/2013) | This is framework contract related to the maintenance of NISR Building including maintenance of Non-ICT equipments like airo conditioners, small works, electricity issues, etc) for a period of 2 years commencing after signing the contract with the Successfull Bidder
July, 2013/Tenders for works
No works
July, 2013/Tenders for consultancy services
17 | Service | Seeking a highly qualified and experienced international firm to provide technical assistance in various statistical areas for a period of three(3) years. | NSDS B.F. | QCBS | Planned and award in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | Planned in the previous fiscal year | End of April 2014 (30/04/2014) | This is Framework Contract for a period of 1 year with a possibility of renewable.This tender was awarded in fiscal year 2012-2013
18 |  | Extension contract for the supervision of works/Refurbishment of NISR building from 30 June to 30th September 2013 | GOR Budget | SSS Method | - | - | - | - | 2013-06-30 | YES | 2013-07-01 | 2013-09-30 | Extension contract for 3 months
19 |  | Recruitment of an International Individual Consultant as Technical Advisor to the Director General of NISR/One year contract period. | NSDS B.F. | IC | 2013-07-01 | 2013-07-05 | 2013-07-23 | 2013-09-14 | 2013-12-03 | No | 2013-12-10 | 2014-12-10 | None
August, 2013/Tenders for goods and non consultancy services
20 |  | Reproduction, Multiplication and Printing of all NISR Publications, Questionnaires, Reports, Magazines, Books, Leaflets, Manuals for different surveys and any other related documents for a period of two(2) years | NSDS Basket Fund Support to NISR | NCB | 2013-08-05 | 2013-08-19 | 2013-09-18 | 2013-10-09 | 2013-12-08 | No | 2013-12-10 | 2014-12-10 | Framework contract for a period of 2 years
August, 2013/Tenders for works
| Works | There is no tenders for works planned to award for August 2013 | - | - | - | - | - | - | - | - | - | - | -
August, 2013/Tenders for consultant services
21 |  | Recruitment of an international individual consultant to conduct the annual review of NSDS1 for the fiscal year 2012-2013 to provide an independent and informed view about its state of affairs. | NSDS B.F. | IC | 2013-08-01 | 2013-08-05 | 2013-08-23 | 2013-09-13 | 2013-09-27 | No | 2013-10-04 | 2013-11-03 | None
22 |  | Contract for consultancy service related to the recruitment of international individual consultant to support NISR in the supervision of the thematic analysis of the Fourth Population and Housing Census. | UNFPA Budget support to NISR and other Budgets allocated to NISR | SSS Method | 2013-08-01 | 2013-08-15 | - | 2013-08-30 | 2013-08-30 | No | 2013-09-03 | 2013-11-02 | No-objection from World Bank may be requested
23 |  | Recruitment of an International Consulting Firm to provide Technical Assistance for the Implementation, Monitoring and Analysis of the Fourth Integrated Household Living Conditions Survey 2013/2014(EICV4) and Statistical Capacity Building on EICV Design, Implementation and Analysis. | NSDS Basket Fund Support to NISR | QCBS | 2013-08-01 | 2013-08-15 | 2014-01-13 | 2014-02-03 | 2014-03-05 | No | 2014-03-19 | 2014-04-18 | For each step we have to request No-Objection to World Bank
September, 2013/Tenders for goods and non consultancy services
24 | Goods | Supply of office stationeries and materials for field workers on regular basis for a period of two(2) years | GOR Budget and other budgets allocated to NISR like NSDS Basket Fund support to NISR | NCB | Planned and award in the previous fiscal year | Planned and award in the previous fiscal year | Planned and award in the previous fiscal year | Planned and award in the previous fiscal year | Planned and award in the previous fiscal year | Planned and award in the previous fiscal year | Planned and award in the previous fiscal year | 2013-09-30 | This is Framework Contract for a period of 2 years. This tender was awarded in fiscal year 2012-2013 but as it will be a continuation for 2 years, means that this fiscal year 2013-2014, we will need a service from the Successful Bidder. So we prefer to plan in this fiscal year for a period one year
25 |  | Provision of insurance services for 38 NISR's Vehicles | GOR Budget and other budgets allocated to NISR like NSDS Basket Fund support to NISR | NCB | Planned and award in the previous fiscal year | Planned and award in the previous fiscal year | Planned and award in the previous fiscal year | Planned and award in the previous fiscal year | Planned and award in the previous fiscal year | Planned and award in the previous fiscal year | Planned and award in the previous fiscal year | 2013-08-15 | This is Framework Contract for a period of 2 years. This tender was awarded in fiscal year 2012-2013 but as it will be a continuation for 2 years, means that this fiscal year 2013-2014, we will need a service from the Successful Bidder. So we prefer to plan in this fiscal year for a period one year
26 |  | Two(2) years on going contract related to supply of ink cartridges and toners for photocopiers and printers used by NISR | GOR Budget and other budgets allocated to NISR like NSDS Basket Fund support to NISR | NCB | Planned and award in the previous fiscal year | Planned and award in the previous fiscal year | Planned and award in the previous fiscal year | Planned and award in the previous fiscal year | Planned and award in the previous fiscal year | Planned and award in the previous fiscal year | Planned and award in the previous fiscal year | 2013-10-15 | This is Framework Contract for a period of 2 years. This tender was awarded in fiscal year 2012-2013 but as it will be a continuation for 2 years, means that this fiscal year 2013-2014, we will need a service from the Successful Bidder. So we prefer to plan in this fiscal year for a period one year
27 |  | Realization and production of publicity spots on radio and TV for sensitization( EICV4, DHS 5, Integrated Business Survey and other surveys conducted by NISR). | GOR Budget and other budgets allocated to NISR like NSDS Basket Fund support to NISR | NCB | Planned and award in the previous fiscal year | Planned and award in the previous fiscal year | Planned and award in the previous fiscal year | Planned and award in the previous fiscal year | Planned and award in the previous fiscal year | Planned and award in the previous fiscal year | Planned and award in the previous fiscal year | 2013-09-30 | This is Framework Contract for a period of 2 years. This tender was awarded in fiscal year 2012-2013 but as it will be a continuation for 2 years, means that this fiscal year 2013-2014, we will need a service from the Successful Bidder. So we prefer to plan in this fiscal year for a period one year
28 |  | Supply of spare parts for repairing fax machine in Central Secretariat by changing fuse, condenser and winding. | GOR budget | Request For Quotation | 2013-09-18 | 2013-09-25 | 2013-09-27 | 2013-10-03 | 2013-10-18 | No | 2013-10-25 | 2013-11-04 | None
29 |  | Supply of cartridges and other ICT materials for NISR Multi Function Printers located in each coridor and other machines | NSDS Basket Fund Support to NISR | RFQ as per WB/PAD | 2013-09-18 | 2013-09-25 | 2013-09-27 | 2013-10-07 | 2013-10-25 | No | 2013-11-05 | 2013-12-20 | None
30 |  | Supply of SIM Cards and Handsets with a Closed User Group(CUG) facility to NISR for a period of Forteen(14) months. | NSDS Basket Fund Support to NISR | RFQ as per WB/PAD | 2013-09-19 | 2013-09-23 | 2013-09-26 | 2013-10-07 | 2013-10-25 | No | 2013-11-05 | 2013-11-21 | None
31 |  | Supply of 446 modems and Airtime cards with six(6) months wireless internet subscription loaded on a monthly basis to be used by district Statisticians and Sector's Civil Registration Officers. | UNFPA | RFQ as per WB/PAD | 2013-09-19 | 2013-09-23 | 2013-09-26 | 2013-10-07 | 2013-11-12 | No | 2013-11-19 | 2013-11-25 | None
32 |  | September, 2013/Tenders for works
| Works | There is no tenders for works planned to award for September 2013 | - | - | - | - | - | - | - | - | - | - | -
September, 2013/Tenders for consultancy services
32 |  | Seeking a National Individual Consultant to Design, Test, Produce, Train Data Managers and Implement the Civil Registration and Vital Statistics Data Collection Web Based Software. | UNFPA | IC | 2013-09-16 | 2013-09-26 | 2013-10-10 | 2013-10-31 | 2013-11-30 | No | 2013-12-09 | 2014-05-30 | None
33 |  | Recruitment of an International Individual Consultant(IT Expert) to Build the Data Processing Systems of Economics Statistics(Data Management and Processing Systems) | AFDB-COMESA Funds | IC | 2013-09-16 | 2013-09-26 | 2013-10-10 | 2013-10-31 | 2013-11-15 | No | 2013-11-22 | 2014-06-15 | None
October, 2013/Tenders for goods and non-consultancy services
34 |  | Supply of electricity cable, repairing mother card for big stabilizers and intervention on big stabilizer Orion 135-25 | GOR Budget | SSS Method | 2013-09-20 | - | - | 2013-09-20 | 2013-09-20 | No | 2013-09-20 | 2013-09-23 | None
35 |  | Supply of three(3) stabilizer mother cards in order to resolve the problem of electricity at NISR offices | GOR Budget | Request For Quotation | 2013-10-04 | 2013-10-07 | 2013-10-10 | 2013-10-20 | 2013-10-25 | No | 2013-10-26 | 2013-10-27 | None
36 |  | Supply of Forty Five(45) sheetings in order to facilitate the transport of EICV4 questionnaires by using NISR vehicles pick-ups 4*4 and protect questionnaires against rain. | GOR Budget | Request For Quotation | 2013-09-30 | 2013-10-01 | 2013-10-04 | 2013-10-20 | 2013-10-25 | No | 2013-10-26 | 2013-10-29 | None
37 |  | Supply of cartridges for IPF Canon 750 to be used for printing of maps of Agricultural Survey 2013-2014 | NSDS Basket Fund Support to NISR | RFQ as per WB/PAD | 2013-10-01 | 2013-10-07 | 2013-10-11 | 2013-10-20 | 2013-10-25 | No | 2013-10-31 | 2013-11-15 | None
38 |  | Supply of One Hundred(100) First Aid Medical Tool Kits for Enumerators of Agricultural Survey | NSDS Basket Fund Support to NISR | RFQ as per WB/PAD | 2013-10-01 | 2013-10-07 | 2013-10-11 | 2013-10-20 | 2013-10-25 | No | 2013-10-31 | 2013-11-15 | None
October, 2013/Tenders for works
39 | works | Extension contract for the supervision of works/Refurbishment of NISR building from 21st October to 20th November 2013 | GOR Budget | SSS Method | - | - | - | - | 2013-10-31 | YES | 2013-10-21 | 2013-11-23 | Extension contract for one month
October, 2013/Tenders for consultancy services
40 |  | Recruitment of International Individual Consultant to Design the Labour Statistics Framework for Rwanda | NSDS Basket Fund Support to NISR | IC | 2013-10-01 | 2013-10-11 | 2013-10-25 | 2013-11-15 | 2013-11-29 | No | 2014-02-17 | 2014-04-30 | None
41 |  | Recruitment of International Individual Consultant For Elaboration of Second National Strategies for the Development of Statistics(NSDS2) 2014-2019 | NSDS Basket Fund Support to NISR | IC | 2013-10-01 | 2013-10-11 | 2013-10-25 | 2013-11-15 | 2013-11-20 | No | 2013-11-30 | 2014-07-15 | None
November, 2013/Tenders for goods and non-consultancy services
42 |  | Supply of three(3) Laptops for infographic competition edition 2013 | NSDS Basket Fund Support to NISR | RFQ as per WB/PAD | 2013-11-05 | 2013-11-15 | 2013-11-18 | 2013-11-20 | 2013-11-20 | No | 2013-11-20 | 2013-11-21 | None
43 |  | Supply of consumables (sugar, milk, Rwandan Tea, Rwanda Coffee, Juices, etc for NISR staff | GOR Budget | NCB | Planned and award in the previous fiscal year | Planned and award in the previous fiscal year | Planned and award in the previous fiscal year | Planned and award in the previous fiscal year | Planned and award in the previous fiscal year | Planned and award in the previous fiscal year | Planned and award in the previous fiscal year | 2013-10-25 | This is Framework Contract for a period of 2 years. This tender was awarded in fiscal year 2012-2013 but as it will be a continuation for 2 years, means that this fiscal year 2013-2014, we will need a service from the Successful Bidder. So we prefer to plan in this fiscal year for a period one year
November, 2013/Tenders for works to be awarded
| Works | There is no tenders for works planned to award for November 2013 | - | - | - | - | - | - | - | - | - | - | -
November, 2013/Tenders for consultant services to be awarded
44 | Services | Contract for consultancy service related to the recruitment of international individual consultant to support NISR in the supervision of the thematic analysis of the Fourth Population and Housing Census. | UNFPA Budget support to NISR | SSS Method | 2013-11-01 | 2013-11-03 | - | 2013-11-04 | 2013-11-04 | No | 2013-11-04 | 2013-12-04 | No-objection from UNFPA dated 31st October 2013
December, 2013/Tenders for goods and non-consultancy services
45 |  | Procurement of insurance of NISR assets-Office equipments, IT equipements, Electronic equipments and Furniture equipments | GOR Budget | NCB | 2013-12-18 | 2013-12-25 | 2014-01-24 | 2014-02-14 | 2014-02-21 | No | 2014-02-28 | 2014-03-15 | None
46 |  | Supply and Assembling of 292 tyres for 58 NISR's Vehicles | NSDS B.F. | NCB | 2013-12-24 | 2013-12-31 | 2014-01-30 | 2014-02-20 | 2014-02-27 | No | 2014-03-06 | 2014-04-20 | None
December, 2013/Tenders for works to be awarded
| Works | There is no tenders for works planned to award for December 2013 | - | - | - | - | - | - | - | - | - | - | None
December, 2013/Tenders for consultancy services to be awarded
|  | There is no tenders for services planned to award for January 2014 | - | - | - | - | - | - | - | - | - | - | None
|  | January, 2014/Tenders for goods and non-consultancy services | [10 empty] | None
47 |  | Provision of insurance services for NISR twenty (20) new vehicles toyota pick-up 4x4 for a period of 6 months | NSDS B.F. | SSS Method | 2014-01-21 | 2014-01-23 | - | 2014-01-30 | 2014-02-04 | No | 2014-02-05 | 2014-08-04 | All vehicles will be insured in one cover wth the same contract end period
48 |  | Internet connectivity, virtual hosting, e-Mails, and Website hosting fees for the fiscal year 2013/2014 | GOR Budget | SSS Method | - | - | - | - | - | - | - | - | Hosting services by RDB
49 |  | Supply of 10 tablets for NISR Top Management and 2 tablets for NISR GIS Team | NSDS B.F. | NCB | 2014-01-24 | 2014-01-31 | 2014-03-02 | 2014-03-23 | 2014-04-13 | No | 2014-04-20 | 2014-06-04 | Tablets to be used by NISR Management Team
50 |  | Supply and installation of two (2) e-DMS scanners | NSDS B.F. | NCB | 2014-01-31 | 2014-02-07 | 2014-03-09 | 2014-03-30 | 2014-04-20 | No | 2014-04-27 | 2014-06-11 | Scanners to be used by NISR Central Secretariat
| Works | January, 2014/Tenders for works
|  | There is no tenders for works planned to award for January 2014 | - | - | - | - | - | - | - | - | - | - | -
January, 2014/Tenders for consultancy services
51 |  | Hiring consulting firm(Contract Extension) for technical assistance, Building the capacity of NISR to produce high quality, sustainable, harmonized and cost-effective of National Accounts and other key Economic Statistics. | NSDS Basket Fund | SSS Method | 2014-01-06 | 2014-01-10 | - | 2014-01-17 | 2014-01-22 | No | 2014-01-27 | 2015-01-27 | A contract extension of one year period may be requested to the Bank
52 | Services | Supply of SPSS and other software including licenses for subscription | NSDS B.F. | NCB | 2014-01-20 | 2014-01-27 | 2014-02-26 | 2014-03-19 | 2014-04-09 | No | 2014-04-16 | 2014-05-31 | Tablets to be used by NISR Management Team
February, 2014/Tenders for goods and non-consultancy services
53 |  | Supply of IT accessories including modems for sections, modems for all Districts, other software, switches, cabling, batteries and other items | GOR Budget | NCB | 2014-02-10 | 2014-02-17 | 2014-03-19 | 2014-04-09 | 2014-04-30 | No | 2014-05-03 | 2014-06-02 | None
54 |  | Procurement of Vehicle Tracking System and maintenance | NSDS B.F. | NCB | 2014-02-14 | 2014-02-21 | 2014-03-23 | 2014-04-13 | 2014-05-04 | No | 2014-05-07 | 2014-06-16 | None
55 |  | Supply of office furniture for NISR staff ( conference round tables, chairs, etc.) | NSDS B.F. | NCB | 2014-02-18 | 2014-02-25 | 2014-03-27 | 2014-04-17 | 2014-05-08 | No | 2014-05-11 | 2014-06-10 | None
56 |  | Recruitment of a company in charge of NISR vehicles cleaning for five(5) years | GOR Budget | NCB | 2014-02-18 | 2014-02-25 | 2014-03-27 | 2014-04-17 | 2014-05-08 | No | 2014-05-11 | 2014-06-10 | None
57 |  | Supply of sport equipments for NISR staff | GOR Budget | NCB | 2014-02-18 | 2014-02-25 | 2014-03-27 | 2014-04-17 | 2014-05-08 | No | 2014-05-11 | 2014-06-10 | None
58 |  | Supply of color printers, 5 external hard Disk and photocopier machine(all in one)-Procurement Team | GOR Budget | NCB | 2014-02-18 | 2014-02-25 | 2014-03-27 | 2014-04-17 | 2014-05-08 | No | 2014-05-11 | 2014-06-10 | None
59 |  | Procurement of shredding machines/binding machines | GOR Budget | Request For Quotation | 2014-02-18 | 2014-02-25 | 2014-03-27 | 2014-04-17 | 2014-05-08 | No | 2014-05-11 | 2014-06-10 | None
60 |  | Supply of curtains for NISR office building. | GOR Budget | NCB | 2014-02-18 | 2014-02-25 | 2014-03-27 | 2014-04-17 | 2014-05-08 | No | 2014-05-11 | 2014-06-10 | None
61 |  | Video conference equipments for NISR training room and NISR board meeting | GOR Budget | NCB | 2014-02-18 | 2014-02-25 | 2014-03-27 | 2014-04-17 | 2014-05-08 | No | 2014-05-11 | 2014-06-10 | None
62 |  | Procurement of security system(entrance access or attendance system, CCTV, fire fighting system, etc) | GOR Budget | NCB | 2014-02-21 | 2014-02-28 | 2014-03-30 | 2014-04-20 | 2014-05-11 | No | 2014-05-14 | 2014-06-13 | None
February, 2014/Tenders for works to be awarded
| Works | There is no tenders for works planned to award for February 2014 | - | - | - | - | - | - | - | - | - | - | -
February, 2014/Tenders for consultancy services to be awarded
63 |  | Recruitment of a firm to enhance NISR corporate image (design and editorial support, etc…….) including production radio and TV programmes | GOR Budget | QCBS | 2014-02-19 | 2014-02-26 | 2014-03-28 | 2014-04-18 | 2014-05-09 | No | 2014-05-12 | 2014-06-11 | None
March, 2014/Tenders for goods and non-consultancy services
64 |  | Procurement of ISIbalo conference materials and printing of NSDS2 with conference to be conducted in July 2014 | NSDS B.F. | NCB | 2014-03-07 | 2014-03-14 | 2014-04-13 | 2014-05-04 | 2014-05-25 | No | 2014-05-28 | 2014-06-27 | None
|  | Providing clearing and forwarding for DHS materials and equipments | DHS Budget | NCB | 2014-03-10 | 2014-03-17 | 2014-04-16 | 2014-05-07 | 2014-05-28 | No | 2014-05-31 | 2014-06-30 | None
March, 2014/Tenders for works to be awarded
|  | There is no tenders for works planned to award for March 2014 | - | - | - | - | - | - | - | - | - | - | -
March, 2014/Tenders for consultancy services to be awarded
|  | Consultancy to review the study and design of NISR Building Refurbishment PHASE II and III, preparation of the tender document, support in selecting the contractor, and supervision of works | - | - | - | - | - | - | - | - | - | - | -
|  | April, 2014/Tenders for goods and non-consultancy services | [10 empty] | -
65 |  | Supply of fuel and gasoline for all NISR vehicles used in the field during the data collection | NSDS B.F. | NCB | 2014-03-17 | 2014-03-24 | 2014-04-23 | 2014-05-14 | 2014-06-04 | No | 2014-06-07 | 2016-06-06 | 2 years contract period
April, 2014/Tenders for works
|  | There is no tenders for works planned to award for April 2014 | - | - | - | - | - | - | - | - | - | - | -
April, 2014/Tenders for consultancy services
There is no tenders for services planned to award for April 2014
May, 2014/Tenders for goods and non-consultancy services
66 |  | Hotel facilities for meetings, workshops, seminars and general meetings with NISR Staff and Stakeholders in various Provinces | NSDS B.F. | NCB | 2014-03-31 | 2014-04-07 | 2014-05-07 | 2014-05-28 | 2014-06-18 | No | 2014-06-21 | 2016-06-20 | 2 years contract period
May, 2014/Tenders for works
|  | There is no tenders for works planned to award for May 2014 | - | - | - | - | - | - | - | - | - | - | -
May, 2014/Tenders for consultancy services
|  | There is no tenders for services planned to award for May 2014 | - | - | - | - | - | - | - | - | - | - | -
June, 2014/Tenders for goods and non-consultancy services
67 |  | Supply and Assembling of tyres for 58 nisr's vehicles | NSDS B.F. | NCB | 2014-06-10 | 2014-06-17 | 2014-07-19 | 2014-08-09 | 2014-08-30 | No | 2014-09-02 | 2014-10-02 | None
68 |  | Insurance for all 58 vehicles used in the field by NISR | NSDS B.F. | NCB | 2014-04-07 | 2014-04-14 | 2014-05-14 | 2014-06-04 | 2014-06-25 | No | 2014-06-28 | 2016-06-27 | 2 years contract period
June, 2014/Tenders for works
|  | There is no tenders for works planned to award for June 2014 | - | - | - | - | - | - | - | - | - | - | -
June, 2014/Tenders for consultancy services
|  | There is no tenders for services planned to award for June 2014 | - | - | - | - | - | - | - | - | - | - | -
TOTAL AMOUNT / From 31st July, 2013 to 30th June, 2014
N.B.:
F.C.: Framework contracts signed by NISR with different partners:
a) NISR has identified through NCB procedures, Hotels/Motels/Training centers in all Provinces and
Districts of Rwanda and Kigali City which may provide the services for a period of two(2) years.
NISR proposes to use those contracts signed for hotels' accomodation expenditures. The selection
of a venue without re-tendering is based on the number of participants to be hosted.
b) For stationeries items, two(2) years contract for future expenditures related to stationaries office
and field supplies was signed with IPN Ltd by taking into account of the unit prices submitted in bid
c) For printing of NISR publication, the contract was also signed with 2 lowest evaluated bidders
d) Repairing of maintenance of NISR vehicles/ framework contract for 2 years
e) cartridges to be replaced in printers, photocopiers, etc./contract of 2 years
f) Cleaning services at NISR building/contract of 2 years
g) Security services at NISR/contract of 2 years
i) Printing of banners, billoards, etc/contract for 2 years
j) Printing of business cards, stamps, etc /contract for 2 years
ABREVIATIONS:
NSDS B.F.: National Statistical Development Strategies Basket Fund
RF: Request for Quotations/Shopping
EOI: Expression Of Interest for services
NCB: National Competitive Bidding
ICB: International Competitive Bidding
RTM : Restricted Tendering Method
QCBS : Quality & Cost Based Selection
SS Or DC: Single Source: Entente Directe ou Marché de Gré à Gré ( Direct Contracting)
OB :Ordinary Budget
NISR : National Institute of Statistics of Rwanda
UNFPA: United Nations Population Fund
UNICEF: United Nations Children's Fund
ADB: African Development Bank
IC: Individual Consultant
CQS: Selection Based on the Consultant’s Qualifications
|  | Revised and Updated on 31st January 2014 by: |  |  | Approved by:
|  | Eric BUGINGO, |  |  | Odette MBABAZI,
|  | Procurement Officer/NISR |  |  | Deputy Director General of Corporate Services/NISR
Formulas:
Planned publication date = [Planned tender document preparation date]+5
Planned bid opening date = [Planned publication date]+30
Planned provisional notification date = [Planned bid opening date]+21
Planned provisional notification date = [Planned publication date]+7
Planned contract signing date = [Planned provisional notification date]+40
Planned contract management start date = [Planned contract signing date]+10
Planned contract closure date = [Planned contract management start date]+30
Note on C14: ebugingo: This is a tender where the Successful Bidder must deliver 190 bags for EICV4 and immediately sign the same contract to supply the related items for a period of 2 years when the needs are required. NISR will consider during the contract period the Unit Prices as per submitted by the Bidder and It can not change any prices during the execution period of contract
Note on E5: ebugingo: During the fiscal year 2012-2013 when we were in the procurement process for hiring the firm, we have been used National Competitive Bidding Method in order to select the Successful Bidder. This is now a framework contract for two years from the date contract was signed by both parties.
Note on E6: ebugingo: During the fiscal year 2012-2013 when we were in the procurement process for hiring the firm, we have been used National Competitive Bidding Method in order to select the Successful Bidder. This is now a framework contract for two years from the date contract was signed by both parties.
Note on E7: ebugingo: During the fiscal year 2012-2013 when we were in the procurement process for hiring the firm, we have been used National Competitive Bidding Method in order to select the Successful Bidder. This is now a framework contract for two years from the date contract was signed by both parties.
Note on E8: ebugingo: During the fiscal year 2012-2013 when we were in the procurement process for hiring the firm, we have been used National Competitive Bidding Method in order to select the Successful Bidder. This is now a framework contract for two years from the date contract was signed by both parties.
Note on E9: ebugingo: During the fiscal year 2012-2013 when we were in the procurement process for hiring the firm, we have been used National Competitive Bidding Method in order to select the Successful Bidder. This is now a framework contract for two years from the date contract was signed by both parties.
Note on E10: ebugingo: During the fiscal year 2012-2013 when we were in the procurement process for hiring the firm, we have been used National Competitive Bidding Method in order to select the Successful Bidder. This is now a framework contract for two years from the date contract was signed by both parties.
Note on E11: ebugingo: During the fiscal year 2012-2013 when we were in the procurement process for hiring the firm, we have been used National Competitive Bidding Method in order to select the Successful Bidder. This is now a framework contract for two years from the date contract was signed by both parties.
Note on E19: ebugingo: During the fiscal year 2012-2013 when we were in the procurement process for hiring the firm, we have been used National Competitive Bidding Method in order to select the Successful Bidder. This is now a framework contract for two years from the date contract was signed by both parties.
Note on E21: ebugingo: This is framework contract related to the maintenance of NISR Building including maintenance of Non-ICT equipments like airo conditioners, small works, electricity issues, etc) for a period of 2 years commencing after signing the contract with the Successfull Bidder
Note on E37: ebugingo: During the fiscal year 2012-2013 when we were in the procurement process for hiring the firm, we have been used National Competitive Bidding Method in order to select the Successful Bidder. This is now a framework contract for two years from the date contract was signed by both parties.
Note on E38: ebugingo: During the fiscal year 2012-2013 when we were in the procurement process for hiring the firm, we have been used National Competitive Bidding Method in order to select the Successful Bidder. This is now a framework contract for two years from the date contract was signed by both parties.
Note on E39: ebugingo: During the fiscal year 2012-2013 when we were in the procurement process for hiring the firm, we have been used National Competitive Bidding Method in order to select the Successful Bidder. This is now a framework contract for two years from the date contract was signed by both parties.
Note on E40: ebugingo: During the fiscal year 2012-2013 when we were in the procurement process for hiring the firm, we have been used National Competitive Bidding Method in order to select the Successful Bidder. This is now a framework contract for two years from the date contract was signed by both parties.
Note on E64: ebugingo: During the fiscal year 2012-2013 when we were in the procurement process for hiring the firm, we have been used National Competitive Bidding Method in order to select the Successful Bidder. This is now a framework contract for two years from the date contract was signed by both parties.
Note on E78: ebugingo: This tender is planned and the procurement process is not required. RDB provide immediately the services to the Procuring Entities.
Note on M20: ebugingo: The expected time for delivery of modems is 29/08/2013 and internet service for 6 months up to the end of March 2014
Note on M27: ebugingo: The date that NISR is expected to receive the final report of the Consultant. This assignment is expected to take a period of one year from the date it's sign the contract.
Note on M29: ebugingo: This is framework contract for 2 years but we will give to the winner first year which will be renewable once based on the performance of successful bidder.
Note on M33: ebugingo: The date that NISR is expected to receive the final report of the Consultant.
Note on M48: ebugingo: The date that NISR is expected to receive the final report of the Consultant is 30 May 2014. This is assignment is expected to start by Middle December 2013 and closed by 30 May 2014.
Note on M49: ebugingo: The date that NISR is expected to receive the final report of the Consultant is 15 June 2014. This is assignment is expected to start by middle November2013 and closed by middle June 2014.
Note on M61: ebugingo: The date that NISR is expected to launch official the NSDS2.
Note on N78: ebugingo: RDB contracted Broad Band Systems Corporation to provide internet services for Government Institutions